## EVACDB
RouteNO | Order | Issue | Portal Route | Location | Treatment Category | MapCode | Treatment | Timeframe | Estimated Cost 1 | Comment
1 | 1 | Capacity | County Route 39 | Corridor Wide | Physical | ‹ | Add "No Parking During Evacuation" Placards | Short | 2400
1 | 2 | Capacity | County Route 39 | Corridor Wide | Physical | ‹ | Widen to 42 feet | Long | 400000
1 | 3 | Capacity | County Route 39 | Corridor Wide | Physical | ‹ | Install Coastal Evacuation Route Signs | Short | 1500
1 | 4 | Capacity | County Route 39 | Corridor Wide | Operational | ‹ | Enforce "No Parking During Evacuations" | During Evacuation | 2300 | Daily
1 | 5 | Capacity | County Route 39 | Corridor Wide | System Management | ‹ | Plan to focus on Intense Inundation Areas | Short | 0
1 | 6 | Flooding | County Route 39 | Flat Creek Bridge | Physical | Œ | New Bridge | Short | 0 | Project is Completed
1 | 7 | Flooding | County Route 39 | East Creek | Physical | Ž | Elevate Roadway, Improve Drainage | Long | 10000000
1 | 8 | Capacity | County Route 39 | Washington Avenue to SR 36 | Physical |  | Hard Running Shoulder | Intermediate | 50000
1 | 9 | Capacity | County Route 39 | Washington Avenue to SR 36 | Physical |  | Relocate Utilities | Intermediate | 35000
1 | 10 | Capacity | County Route 39 | Hemlock Street | Operational |  | Two-phase signal during evacuations. Divert NB Traffic. | During Evacuations | 4000 | Daily
1 | 11 | Flooding | County Route 39 | SR 36/Union Ave | Technological |  | LED and Backup Power for Signals | Intermediate | 7000 | location
1 | 12 | Flooding | County Route 39 | SR 36/Union Ave | Technological |  | Upgrade signals for wireless control | Intermediate | 23000 | location
2 | 13 | Capacity | CR 56/CR 7 | Corridor Wide | Physical | ‹ | Add "No Parking During Evacuation" Placards | Short | 1400
2 | 14 | Capacity | CR 56/CR 7 | Corridor Wide | Physical | ‹ | Install Coastal Evacuation Route Signing at Critical Intersections | Short | 2000
2 | 15 | Capacity | CR 56/CR 7 | Corridor Wide | Operational | ‹ | Enforce "No Parking During Evacuations" | During Evacuation | 2000
2 | 16 | Capacity | CR 56/CR 7 | Corridor Wide | Operational | ‹ | Coordinate Existing Highway Advisory System | Short | 0
2 | 17 | Flooding | CR 56/CR 7 | Corridor Wide | System Management | ‹ | Plan to focus on Intense Inundation Areas | During Evacuation | 0
2 | 18 | Capacity | CR 56/CR 7 | Carr Ave | Operational | Œ | Close Circuit Street | During Evacuation | 1000 | Daily
2 | 19 | Capacity | CR 56/CR 7 | Carr Ave | Physical |  | Re-stripe | Short | 27000
2 | 20 | Capacity | CR 56/CR 7 | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | LED and Backup Power for Signals | Intermediate | 21000 | Location
2 | 21 | Capacity | CR 56/CR 7 | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | Upgrade signals for wireless control | Intermediate | 69000 | Location
2 | 22 | Capacity | CR 56/CR 7 | Church St. | Operational |  | Use parking lane as a through street - Police | During Evacuation | 500 | Daily
2 | 23 | Capacity | CR 56/CR 7 | Main St./Henry Hudson Bike Trail | Operational |  | Control Crossing Using Police | During Evacuation | 500 | Daily
2 | 24 | Capacity | CR 56/CR 7 | Main St./SR 36 | Physical | ‘ | Widen to create full shoulder | Intermediate | 300000
2 | 25 | Capacity | CR 56/CR 7 | Main St./SR 36 | Operational | ‘ | Control Crossing Using Police | During Evacuation | 500 | Daily
3 | 26 | Capacity | SR 36 (N) | Corridor Wide | Physical | ‹ | Widen WB roadway to create a full shoulder | Long | 30000000
3 | 27 | Capacity | SR 36 (N) | Corridor Wide | Physical | ‹ | Add "No Parking During Evacuation" Placards | Short | 10400
3 | 28 | Capacity | SR 36 (N) | Corridor Wide | Operational | ‹ | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
3 | 29 | Capacity | SR 36 (N) | Corridor Wide | Operational | ‹ | Emergency Service Patrols | During Evacuation | 5000 | Daily
3 | 30 | Capacity | SR 36 (N) | Corridor Wide | Technological | ‹ | LED and Backup Power for Signals | Intermediate | 154000
3 | 31 | Capacity | SR 36 (N) | Corridor Wide | Technological | ‹ | Upgrade signals for wireless control | Intermediate | 506000
3 | 32 | Capacity | SR 36 (N) | Corridor Wide | Operational | ‹ | Coordinate Existing Highway Advisory System | Short | 0
3 | 33 | Capacity | SR 36 (N) | Corridor Wide | System Management | ‹ | Plan to focus on Intense Inundation Areas | Short | 0
3 | 34 | Capacity | SR 36 (N) | Highlands/Sea Bright | Physical | Œ | New Bridge | Under Construction | 0
3 | 35 | Capacity | SR 36 (N) | CR8A | Physical |  | Install Dynamic Message Sign | Intermediate | 30000
3 | 36 | Capacity | SR 36 (N) | CR 8A | Physical | Ž | Reconfigure Intersection | Long | 170000
3 | 37 | Capacity | SR 36 (N) | Normandy Road Underpass | Physical | ‘ | Create one-lane bypass under bridge | Intermediate | 600000
3 | 38 | Capacity | SR 36 (N) | Broad Street | Physical | ’ | Widen at Intersection | Intermediate | 4000000 | refig
3 | 39 | Flooding | SR 36 (N) | Lupatatong Creek | Physical |  | Elevate Roadway, Improve Drainage | Long | 6500000
3 | 40 | Flooding | SR 36 (N) | Many Mind / Wagner Creek | Physical |  | Elevate Roadway, Improve Drainage | Intermediate | 6500000 | refig
4 | 41 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | ‹ | Widen WB roadway to create a full shoulder | Long | 6000000 | Not including Harmony Road (below)
4 | 42 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | ‹ | Add "No Parking During Evacuation" Placards | Short | 2100
4 | 43 | Capacity | CR 516/ CR 50 | Corridor Wide | Operational | ‹ | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
4 | 44 | Capacity | CR 516/ CR 50 | Corridor Wide | Operational | ‹ | Emergency Service Patrols | During Evacuation | 5000 | Daily
4 | 45 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | ‹ | Add Evacuation Route signing at key locations | Short | 1600
4 | 46 | Capacity | CR 516/ CR 50 | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | LED and Backup Power for Signals | Intermediate | 28000
4 | 47 | Capacity | CR 516/ CR 50 | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | Upgrade signals for wireless control | Intermediate | 92000
4 | 48 | Capacity | CR 516/ CR 50 | Church Street | Operational |  | Close a portion of Church Street in the SB Direction, Install temporary detour signs | During Evacuation | 2000
4 | 49 | Capacity | CR 516/ CR 50 | SR 35 / CR 50 | Physical |  | Widen roadbed between CR 50 and Harmony Road | Long | 1500000
4 | 50 | Capacity | CR 516/ CR 50 | Parking Lot, SR 36 | Operational | Ž | Close southerly driveway entrance | During Evacuation | 500
5 | 51 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Physical | ‹ | Widen WB roadway to create a full shoulder | Long | 12500000
5 | 52 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Physical | ‹ | Install Coastal Evacuation Route signing throughout route | Short | 4500
5 | 53 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Operational | ‹ | Emergency Service Patrols | During Evacuation | 5000
5 | 54 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Operational | ‹ | Enforce "No Parking During Evacuations" | During Evacuation | 2000
5 | 55 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Technological | ‹ | LED and Backup Power for Signals | Intermediate | 42000
5 | 56 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Technological | ‹ | Upgrade signals for wireless control | Intermediate | 138000
5 | 57 | Flooding | CR 8A / 12A / 12 | Corridor Wide | System Management | ‹ | Plan to focus on Intense Inundation Areas | During Evacuation | 0
5 | 58 | Capacity | CR 8A / 12A / 12 | Oceanic Bridge | Physical | Œ | Reconstruct Bridge | Long | 50000000
5 | 59 | Capacity | CR 8A / 12A / 12 | NJ GSP Exit 114 | Operational |  | Close connecting ramp between GSP on-and off ramps; reverse GSP southbound Exit Ramp to Red Hill Rd. | During Evacuation | 8000 | Daily
5 | 60 | Capacity | CR 8A / 12A / 12 | NJ GSP Exit 114 | System Management | Ž | Coordinate GSP ramp reversal activities with NJOEM and NJDOT | Short | 0
6 | 61 | Capacity | CR 520 | Corridor Wide | Physical | ‹ | Widen WB roadway to create a full shoulder | Long | 16500000
6 | 62 | Capacity | CR 520 | Corridor Wide | Operational | ‹ | Initiate Emergency Service Patrol Program | During Evacuation | 4000 | Daily
6 | 63 | Capacity | CR 520 | Corridor Wide | Technological | ‹ | LED and Backup Power for Signals | Intermediate | 70000
6 | 64 | Capacity | CR 520 | Corridor Wide | Technological | ‹ | Upgrade signals for wireless control | Intermediate | 230000
6 | 65 | Capacity | CR 520 | Corridor Wide | System Management | ‹ | Plan to focus on Intense Inundation Areas | Short | 0
6 | 66 | Capacity | CR 520 | Rumson Bridge | Physical | Œ | Widen Bridge to 42 feet | Intermediate | 500000
6 | 67 | Capacity | CR 520 | Rumson Bridge | System Management | Œ | Coordinate evacuation planning initiatives with NJTPA activities associated with the Rumson Rd. over Shrewsbury River Study | Short | 0
6 | 68 | Capacity | CR 520 | Pinckney Road | Physical |  | Add "No Parking During Evacuation" Placards | Short | 6000
6 | 69 | Capacity | CR 520 | Pinckney Road | Operational |  | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
6 | 70 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Physical | Ž | Major capital improvement connecting Rumson Rd. and Newman Springs Rd. | Long | 30000000
6 | 71 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | System Management | Ž | Coordinate road enhancement program in the vicinity of the Broad Street / SR 35 Intersection. | Intermediate | 0
6 | 72 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Detour Rumson Rd. WB traffic to White Rd. and SR 35 NB to access Newman Springs Rd. and provide "Alt" Signing | During Evacuation | 2000
6 | 73 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Upgrade White Rd., as necessary to function as a portal section and install Coastal Evacuation route signs | Long | 1900000
6 | 74 | Capacity | CR 520 | NJ GSP Exit 109 SB entrance ramp | Physical |  | Construct cross-over ramp section that would connect GSP SB entrance ramp to the GSP SB exit ramp; reverse direction of exit ramp from SB to NB | Intermediate | 198000
6 | 75 | Capacity | CR 520 | NJ GSP Exit 109 SB entrance ramp | Operational |  | Close ramp, provide police enforcement | During Evacuation | 5000 | Daily
6 | 76 | Capacity | CR 520 | NJ GSP Exit 109 | System Management |  | Coordinate GSP ramp reversal activities with NJOEM and NJDOT | Short | 0
7 | 77 | Capacity | SR 36 (Central) | Corridor Wide | Physical | ‹ | Widen WB roadway to create a full shoulder | Long | 14000000
7 | 78 | Capacity | SR 36 (Central) | Corridor Wide | Physical | ‹ | Add "No Parking During Evacuation" Placards | Short | 5000
7 | 79 | Capacity | SR 36 (Central) | Corridor Wide | Operational | ‹ | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
7 | 80 | Capacity | SR 36 (Central) | Corridor Wide | Operational | ‹ | Emergency Service Patrols | During Evacuation | 4000 | Daily
7 | 81 | Capacity | SR 36 (Central) | Corridor Wide | Technological | ‹ | LED and Backup Power for Signals | Intermediate | 98000
7 | 82 | Capacity | SR 36 (Central) | Corridor Wide | Technological | ‹ | Upgrade signals for wireless control | Intermediate | 322000
7 | 83 | Capacity | SR 36 (Central) | Corridor Wide | System Management | ‹ | Plan to focus on Intense Inundation Areas | Short | 0
7 | 84 | Capacity | SR 36 (Central) | SR 36 between Clifton Ave. and Washington Street | Physical | Œ | RE-stripe to provide one additional WB lane | Short | 30000
7 | 85 | Capacity | SR 36 (Central) | SR 36/Florence Ave. unsignalized intersection | Operational |  | Deploy police resources | During Evacuation | 500 | Daily
7 | 86 | Capacity | SR 36 (Central) | Florence Ave. between MacArthur Ave. and SR 36 | Operational |  | Close Florence Close Florence Ave. SB between MacArthur Way and SR 36 (option to deploying police as above) | During Evacuation | 0
7 | 87 | Capacity | SR 36 (Central) | Bridge over Troutmans Creek | Physical | Ž | Option - Widen Bridge to 42 feet and provide one travel lane and full hard running shoulder in each direction | Long | 44000
7 | 88 | Capacity | SR 36 (Central) | SR 36 connections at Clifton Ave., Long Branch Ave., Liberty St., Rockwell Ave., Seventh Ave., Washington St. | Operational |  | Prohibit left-turn in WB direction; deploy police at each intersection. | During Evacuation | 3000 | Daily
7 | 89 | Capacity | SR 36 (Central) | At-grade RR crossing near Washington St. | System Management |  | Coordinate portal improvements near RR crossing with NJ Transit | Long | 0
7 | 90 | Flooding | SR 36 (Central) | (MP 4.4 to MP5.5 - Long Branch Ave.) | System Management |  | Coordinate this future candidate drainage project with NJ Transit | Long | 0
7 | 91 | Capacity | SR 36 (Central) | SR 36 between Branchport Ave. and Victor Ave. | Operational |  | Create two temporary WB lanes using traffic control devices and deployment of police. | During Evacuation | 1000
7 | 92 | Capacity | SR 36 (Central) | SR 36 between Washington St. and Victor Ave. | Operational | ‘ | Narrow grassy median, install third WB travel lane | Long | 5000000
7 | 93 | Capacity | SR 36 (Central) | NJ GSP Exit105 | Operational | ’ | Reverse direction and function of GSP Exit ramp to SR 36 EB; make it an on-ramp to GSP and change its direction from SB to NB | Short | 5000 | Daily
8 | 94 | Capacity | Park Ave. | Corridor Wide | Physical | ‹ | Widen WB roadway to create a full shoulder | Long | 3300000
8 | 95 | Capacity | Park Ave. | Corridor Wide | Physical | ‹ | Add "No Parking During Evacuation" Placards | Short | 2400
8 | 96 | Capacity | Park Ave. | Corridor Wide | Physical | ‹ | Install Coastal Evacuation Route signing throughout route | Short | 8000
8 | 97 | Capacity | Park Ave. | Corridor Wide | Operational | ‹ | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
8 | 98 | Capacity | Park Ave. | Corridor Wide | Operational | ‹ | Emergency Service Patrols | During Evacuation | 5000
8 | 99 | Capacity | Park Ave. | Corridor Wide | Operational | ‹ | Coordinate Highway Advisory Radio Messages through nearby systems | Short | 0
8 | 100 | Capacity | Park Ave. | Corridor Wide | System Management | ‹ | Where appropriate, coordinate corridor improvments with NJTPA 2030 Plan intiatives | Long | 0
8 | 101 | Capacity | Park Ave. | Corridor Wide | System Management | ‹ | Provide evacuees with emergency information through a public communication program | Short | 0
8 | 101.5 | Capacity | Park Ave. | NJ Coast Line Crossing, West of Lincoln Ave. | System Management | Œ | Coordinate improvements with NJ Transit to account for Evacuation | Long | 0
8 | 102 | Capacity | Park Ave. | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Technological |  | Provide Portable Traffic Signals | Intermediate | 60000
8 | 103 | Capacity | Park Ave. | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Operational |  | Provide police enforcement | During Evacuation | 4000 | Daily
8 | 104 | Capacity | Park Ave. | Corridor Wide | Technological | Ž | LED and Backup Power for Signals | Intermediate | 35000
8 | 105 | Capacity | Park Ave. | Corridor Wide | Technological | Ž | Upgrade signals for wireless control | Intermediate | 115000
9 | 106 | Capacity | CR 16 | Corridor Wide | Physical | ‹ | Widen to create full shoulder | Long | 9000000
9 | 107 | Capacity | CR 16 | Corridor Wide | Physical | ‹ | Add "No Parking During Evacuation" Placards | Short | 3400
9 | 108 | Capacity | CR 16 | Corridor Wide | Operational | ‹ | Emergency Service Patrols | During Evacuation | 5000 | Daily
9 | 109 | Capacity | CR 16 | Corridor Wide | Operational | ‹ | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
9 | 110 | Capacity | CR 16 | Corridor Wide | Technological | ‹ | LED and Backup Power for Signals | Intermediate | 105000
9 | 111 | Capacity | CR 16 | Corridor Wide | Technological | ‹ | Upgrade signals for wireless control | Intermediate | 345000
9 | 112 | Capacity | CR 16 | Corridor Wide | System Management | ‹ | Provide Highway Advisory Radio for this and other nearby corridors | Intermediate | 35000
9 | 113 | Capacity | CR 16 | Seaview Sq. Mall entrances to CR 16 | Operational | Œ | Allow only one exit ramp from the mall onto CR 16 | During Evacuation | 5000 | Daily
9 | 114 | Capacity | CR 16 | Wayside Rd. to Jumping Brook Rd. | Physical |  | Widen State Route 66 | Long | 3800000
9 | 115 | Capacity | CR 16 | Asbury Park between Essex Rd. and Green Grove Rd. | Operational | Ž | Close business driveways located on south side of Asbury Ave. Provide police enforcement | During Evacuation | 2000 | Daily
9 | 116 | Capacity | CR 16 | Asbury Ave./Essex Rd. unsignalized intersection | Technological |  | Provide Portable Traffic Signals | Intermediate | 60000
9 | 117 | Capacity | CR 16 | Asbury Ave./Essex Rd. unsignalized intersection | Operational |  | Provide police enforcement | During Evacuation | 2000 | Daily
9 | 118 | Capacity | CR 16 | NJ GSP Exit 102 | Operational |  | Close GSP entrance ramp and reverse direction of GSP exit ramp; provide police enforcement | During Evacuation | 2000 | Daily
9 | 119 | Capacity | CR 16 | CR 16/Foxchase Drive unsignalized intersection | Operational | ‘ | Provide police enforcement | During Evacuation | 2000 | Daily
9 | 120 | Capacity | CR 16 | CR 16/CR 547 intersection | Physical | ’ | Widen CR 16 westbound approach to provide full shoulder; also widen intersection's west leg to provide two departure lanes | Long | 500000
10 | 121 | Capacity | SR 33 | Corridor Wide | Physical | ‹ | Widen to create full shoulder | Long | 10000000
10 | 122 | Capacity | SR 33 | Corridor Wide | Physical | ‹ | Add "No Parking During Evacuation" Placards | Short | 3700
10 | 123 | Capacity | SR 33 | Corridor Wide | Operational | ‹ | Enforce "No Parking During Evacuations" | During Evacuations | 2000 | Daily
10 | 124 | Capacity | SR 33 | Corridor Wide | Operational | ‹ | Emergency Service Patrols | During Evacuations | 5000 | Daily
10 | 125 | Capacity | SR 33 | Corridor Wide | Technological | ‹ | LED and Backup Power for Signals | Intermediate | 105000
10 | 126 | Capacity | SR 33 | Corridor Wide | Technological | ‹ | Upgrade signals for wireless control | Intermediate | 345000
10 | 127 | Capacity | SR 33 | Corridor Wide | System Management | ‹ | Plan to focus on Intense Inundation Areas | During Evacuation | 0
10 | 128 | Capacity | SR 33 | Corridor Wide | System Management | ‹ | Institute public communication program through multi-media sources to provide evacuees with information about emergency shelters | During Evacuation | 0
10 | 129 | Capacity | SR 33 | Corridor Wide | Physical | ‹ | Promote coordination with the new HAR proposed for Neptune in this report. | Intermediate | 0
10 | 130 | Capacity | SR 33 | SR 33 WB between Atkins Ave. and Myrtle Ave. | Physical | Œ | Provide second westbound lane thorugh a combination of pavement re-striping, narrowing center median, and realigning sidewalk | Long | 250000
10 | 131 | Capacity | SR 33 | SR 33 at NJ GSP Exit 100A | Physical |  | Construct crossover between GSP on-ramp and exit ramp | Long | 750000
10 | 132 | Capacity | SR 33 | SR 33 at NJ GSP Exit 100A | Operational |  | Provide police enforcement | During Evacuation | 4000 | Daily
11 | 133 | Capacity | CR 524 (Allaire) | Corridor Wide | Physical | ‹ | Widen WB roadway to create a full shoulder | Long | 7700000
11 | 134 | Capacity | CR 524 (Allaire) | Corridor Wide | Physical | ‹ | Add "No Parking During Evacuation" Placards | Short | 3000
11 | 135 | Capacity | CR 524 (Allaire) | Corridor Wide | Operational | ‹ | Emergency Service Patrols | During Evacuation | 5000 | Daily
11 | 136 | Capacity | CR 524 (Allaire) | Corridor Wide | Operational | ‹ | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
11 | 137 | Capacity | CR 524 (Allaire) | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | LED and Backup Power for Signals | Intermediate | 21000
11 | 138 | Capacity | CR 524 (Allaire) | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | Upgrade signals for wireless control | Intermediate | 69000
11 | 139 | Capacity | CR 524 (Allaire) | SR 34, between Traffic Circle and Allenwood Rd. | Physical | Ž | Install third travel lane in northbound direction between traffic circle and Allenwood Rd. | Long | 1100000
11 | 140 | Capacity | CR 524 (Allaire) | SR 34 Traffic Circle | Physical |  | Convert traffic circle into signalized intersection | Long | 10000000
11 | 141 | Capacity | CR 524 (Allaire) | Cr 524/Allenwood Rd./Ridgewood Rd. | Operational |  | Control traffic flow using police | During Evacuation | 500 | Daily
11 | 142 | Capacity | CR 524 (Allaire) | Cr 524/Allenwood Rd./Ridgewood Rd. | Technological |  | Install flashing beacons to control traffic flow through intersection | Short | 10000
12 | 143 | Capacity | CR 524 Spur | Corridor Wide | Physical | ‹ | Widen WB roadway to create a full shoulder | Long | 8800000
12 | 144 | Capacity | CR 524 Spur | Corridor Wide | Physical | ‹ | Add "No Parking During Evacuation" Placards | Short | 3200
12 | 145 | Capacity | CR 524 Spur | Corridor Wide | Operational | ‹ | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | na
12 | 146 | Capacity | CR 524 Spur | Corridor Wide | Operational | ‹ | Emergency Service Patrols | During Evacuation | 5000 | Daily
12 | 147 | Capacity | CR 524 Spur | CR 20 (Broad Street) | Technological | Œ | LED and Backup Power for Signals | Intermediate | 7000
12 | 148 | Capacity | CR 524 Spur | CR 20 (Broad Street) | Technological | Œ | Upgrade signals for wireless control | Intermediate | 23000
12 | 149 | Capacity | CR 524 Spur | SR 35/CR 524 Spur Traffic Circle | Physical |  | Eliminate traffic circle | Long | 10000000
12 | 150 | Capacity | CR 524 Spur | Tilton Corner Road | Operational | Ž | Close road and detour traffic to Ridgewood Road | During Evacuation | 4000 | Daily
12 | 151 | Capacity | CR 524 Spur | CR 524 Spur at Ramshorn Drive | Operational |  | Deploy police at unsignalized intersection | During Evacuation | 500 | Daily
[6 empty] |  | 140

## Corridor Improvements
RouteNO | Portal Route | Treatment
1 | County Route 39 | Add "No Parking During Evacuation" Placards
1 | County Route 39 | Widen to 42 feet
1 | County Route 39 | Install Coastal Evacuation Route Signs
1 | County Route 39 | Enforce "No Parking During Evacuations"
1 | County Route 39 | Plan to focus on Intense Inundation Areas
2 | CR 56/CR 7 | Add "No Parking During Evacuation" Placards
2 | CR 56/CR 7 | Install Coastal Evacuation Route Signing at Critical Intersections
2 | CR 56/CR 7 | Enforce "No Parking During Evacuations"
2 | CR 56/CR 7 | Coordinate Existing Highway Advisory System
2 | CR 56/CR 7 | Plan to focus on Intense Inundation Areas
3 | SR 36 (N) | Widen WB roadway to create a full shoulder
3 | SR 36 (N) | Add "No Parking During Evacuation" Placards
3 | SR 36 (N) | Enforce "No Parking During Evacuations"
3 | SR 36 (N) | Emergency Service Patrols
3 | SR 36 (N) | LED and Backup Power for Signals
3 | SR 36 (N) | Upgrade signals for wireless control
3 | SR 36 (N) | Coordinate Existing Highway Advisory System
3 | SR 36 (N) | Plan to focus on Intense Inundation Areas
4 | CR 516/ CR 50 | Widen WB roadway to create a full shoulder
4 | CR 516/ CR 50 | Add "No Parking During Evacuation" Placards
4 | CR 516/ CR 50 | Enforce "No Parking During Evacuations"
4 | CR 516/ CR 50 | Emergency Service Patrols
4 | CR 516/ CR 50 | Add Evacuation Route signing at key locations
5 | CR 8A / 12A / 12 | Widen WB roadway to create a full shoulder
5 | CR 8A / 12A / 12 | Install Coastal Evacuation Route signing throughout route
5 | CR 8A / 12A / 12 | Emergency Service Patrols
5 | CR 8A / 12A / 12 | Enforce "No Parking During Evacuations"
5 | CR 8A / 12A / 12 | LED and Backup Power for Signals
5 | CR 8A / 12A / 12 | Upgrade signals for wireless control
5 | CR 8A / 12A / 12 | Plan to focus on Intense Inundation Areas
6 | CR 520 | Widen WB roadway to create a full shoulder
6 | CR 520 | Initiate Emergency Service Patrol Program
6 | CR 520 | LED and Backup Power for Signals
6 | CR 520 | Upgrade signals for wireless control
6 | CR 520 | Plan to focus on Intense Inundation Areas
7 | SR 36 (Central) | Widen WB roadway to create a full shoulder
7 | SR 36 (Central) | Add "No Parking During Evacuation" Placards
7 | SR 36 (Central) | Enforce "No Parking During Evacuations"
7 | SR 36 (Central) | Emergency Service Patrols
7 | SR 36 (Central) | LED and Backup Power for Signals
7 | SR 36 (Central) | Upgrade signals for wireless control
7 | SR 36 (Central) | Plan to focus on Intense Inundation Areas
8 | Park Ave. | Widen WB roadway to create a full shoulder
8 | Park Ave. | Add "No Parking During Evacuation" Placards
8 | Park Ave. | Install Coastal Evacuation Route signing throughout route
8 | Park Ave. | Enforce "No Parking During Evacuations"
8 | Park Ave. | Emergency Service Patrols
8 | Park Ave. | Coordinate Highway Advisory Radio Messages through nearby systems
8 | Park Ave. | Where appropriate, coordinate corridor improvments with NJTPA 2030 Plan intiatives
8 | Park Ave. | Provide evacuees with emergency information through a public communication program
9 | CR 16 | Widen to create full shoulder
9 | CR 16 | Add "No Parking During Evacuation" Placards
9 | CR 16 | Emergency Service Patrols
9 | CR 16 | Enforce "No Parking During Evacuations"
9 | CR 16 | LED and Backup Power for Signals
9 | CR 16 | Upgrade signals for wireless control
9 | CR 16 | Provide Highway Advisory Radio for this and other nearby corridors
10 | SR 33 | Widen to create full shoulder
10 | SR 33 | Add "No Parking During Evacuation" Placards
10 | SR 33 | Enforce "No Parking During Evacuations"
10 | SR 33 | Emergency Service Patrols
10 | SR 33 | LED and Backup Power for Signals
10 | SR 33 | Upgrade signals for wireless control
10 | SR 33 | Plan to focus on Intense Inundation Areas
10 | SR 33 | Institute public communication program through multi-media sources to provide evacuees with information about emergency shelters
10 | SR 33 | Promote coordination with the new HAR proposed for Neptune in this report.
11 | CR 524 (Allaire) | Widen WB roadway to create a full shoulder
11 | CR 524 (Allaire) | Add "No Parking During Evacuation" Placards
11 | CR 524 (Allaire) | Emergency Service Patrols
11 | CR 524 (Allaire) | Enforce "No Parking During Evacuations"
12 | CR 524 Spur | Widen WB roadway to create a full shoulder
12 | CR 524 Spur | Add "No Parking During Evacuation" Placards
12 | CR 524 Spur | Enforce "No Parking During Evacuations"
12 | CR 524 Spur | Emergency Service Patrols

## EVACDB2
RouteNO | Order | Issue | Portal Route | Location | Treatment Category | MapCode | Treatment | Timeframe | Estimated Cost 1 | Comment
1 | 1 | Capacity | County Route 39 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2400
1 | 2 | Capacity | County Route 39 | Corridor Wide | Physical | NA | Widen to 42 feet | Long | 400000
1 | 3 | Capacity | County Route 39 | Corridor Wide | Physical | NA | Install Coastal Evacuation Route Signs | Short | 1500
1 | 4 | Capacity | County Route 39 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2300 | Daily
1 | 5 | Capacity | County Route 39 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0
1 | 6 | Flooding | County Route 39 | Flat Creek Bridge | Physical | Œ | New Bridge | Short | 0 | Project is Completed
1 | 7 | Flooding | County Route 39 | East Creek | Physical | Ž | Elevate Roadway, Improve Drainage | Long | 10000000
1 | 8 | Capacity | County Route 39 | Washington Avenue to SR 36 | Physical |  | Hard Running Shoulder | Intermediate | 50000
1 | 9 | Capacity | County Route 39 | Washington Avenue to SR 36 | Physical |  | Relocate Utilities | Intermediate | 35000
1 | 10 | Capacity | County Route 39 | Hemlock Street | Operational |  | Two-phase signal during evacuations. Divert NB Traffic. | During Evacuations | 4000 | Daily
1 | 11 | Flooding | County Route 39 | SR 36/Union Ave | Technological |  | LED and Backup Power for Signals | Intermediate | 7000 | location
1 | 12 | Flooding | County Route 39 | SR 36/Union Ave | Technological |  | Upgrade signals for wireless control | Intermediate | 23000 | location
2 | 13 | Capacity | CR 56/CR 7 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 1400
2 | 14 | Capacity | CR 56/CR 7 | Corridor Wide | Physical | NA | Install Coastal Evacuation Route Signing at Critical Intersections | Short | 2000
2 | 15 | Capacity | CR 56/CR 7 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000
2 | 16 | Capacity | CR 56/CR 7 | Corridor Wide | Operational | NA | Coordinate Existing Highway Advisory System | Short | 0
2 | 17 | Flooding | CR 56/CR 7 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0
2 | 18 | Capacity | CR 56/CR 7 | Carr Ave | Operational | Œ | Close Circuit Street | During Evacuation | 1000 | Daily
2 | 19 | Capacity | CR 56/CR 7 | Carr Ave | Physical |  | Re-stripe | Short | 27000
2 | 20 | Capacity | CR 56/CR 7 | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | LED and Backup Power for Signals | Intermediate | 21000 | Location
2 | 21 | Capacity | CR 56/CR 7 | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | Upgrade signals for wireless control | Intermediate | 69000 | Location
2 | 22 | Capacity | CR 56/CR 7 | Church St. | Operational |  | Use parking lane as a through street - Police | During Evacuation | 500 | Daily
2 | 23 | Capacity | CR 56/CR 7 | Main St./Henry Hudson Bike Trail | Operational |  | Control Crossing Using Police | During Evacuation | 500 | Daily
2 | 24 | Capacity | CR 56/CR 7 | Main St./SR 36 | Physical | ‘ | Widen to create full shoulder | Intermediate | 300000
2 | 25 | Capacity | CR 56/CR 7 | Main St./SR 36 | Operational | ‘ | Control Crossing Using Police | During Evacuation | 500 | Daily
3 | 26 | Capacity | SR 36 (N) | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 30000000
3 | 27 | Capacity | SR 36 (N) | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 10400
3 | 28 | Capacity | SR 36 (N) | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
3 | 29 | Capacity | SR 36 (N) | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Daily
3 | 30 | Capacity | SR 36 (N) | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 154000
3 | 31 | Capacity | SR 36 (N) | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 506000
3 | 32 | Capacity | SR 36 (N) | Corridor Wide | Operational | NA | Coordinate Existing Highway Advisory System | Short | 0
3 | 33 | Capacity | SR 36 (N) | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0
3 | 34 | Capacity | SR 36 (N) | Highlands/Sea Bright | Physical | Œ | New Bridge | Under Construction | 0
3 | 35 | Capacity | SR 36 (N) | CR8A | Physical |  | Install Dynamic Message Sign | Intermediate | 30000
3 | 36 | Capacity | SR 36 (N) | CR 8A | Physical | Ž | Reconfigure Intersection | Long | 170000
3 | 37 | Capacity | SR 36 (N) | Normandy Road Underpass | Physical | ‘ | Create one-lane bypass under bridge | Intermediate | 600000
3 | 38 | Capacity | SR 36 (N) | Broad Street | Physical | ’ | Widen at Intersection | Intermediate | 4000000 | refig
3 | 39 | Flooding | SR 36 (N) | Lupatatong Creek | Physical |  | Elevate Roadway, Improve Drainage | Long | 6500000
3 | 40 | Flooding | SR 36 (N) | Many Mind / Wagner Creek | Physical |  | Elevate Roadway, Improve Drainage | Intermediate | 6500000 | refig
4 | 41 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 6000000 | Not including Harmony Road (below)
4 | 42 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2100
4 | 43 | Capacity | CR 516/ CR 50 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
4 | 44 | Capacity | CR 516/ CR 50 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Daily
4 | 45 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | NA | Add Evacuation Route signing at key locations | Short | 1600
4 | 46 | Capacity | CR 516/ CR 50 | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | LED and Backup Power for Signals | Intermediate | 28000
4 | 47 | Capacity | CR 516/ CR 50 | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | Upgrade signals for wireless control | Intermediate | 92000
4 | 48 | Capacity | CR 516/ CR 50 | Church Street | Operational |  | Close a portion of Church Street in the SB Direction, Install temporary detour signs | During Evacuation | 2000
4 | 49 | Capacity | CR 516/ CR 50 | SR 35 / CR 50 | Physical |  | Widen roadbed between CR 50 and Harmony Road | Long | 1500000
4 | 50 | Capacity | CR 516/ CR 50 | Parking Lot, SR 36 | Operational | Ž | Close southerly driveway entrance | During Evacuation | 500
5 | 51 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 12500000
5 | 52 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Physical | NA | Install Coastal Evacuation Route signing throughout route | Short | 4500
5 | 53 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000
5 | 54 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000
5 | 55 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 42000
5 | 56 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 138000
5 | 57 | Flooding | CR 8A / 12A / 12 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0
5 | 58 | Capacity | CR 8A / 12A / 12 | Oceanic Bridge | Physical | Œ | Reconstruct Bridge | Long | 50000000
5 | 59 | Capacity | CR 8A / 12A / 12 | NJ GSP Exit 114 | Operational |  | Close connecting ramp between GSP on-and off ramps; reverse GSP southbound Exit Ramp to Red Hill Rd. | During Evacuation | 8000 | Daily
5 | 60 | Capacity | CR 8A / 12A / 12 | NJ GSP Exit 114 | System Management | Ž | Coordinate GSP ramp reversal activities with NJOEM and NJDOT | Short | 0
6 | 61 | Capacity | CR 520 | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 16500000
6 | 62 | Capacity | CR 520 | Corridor Wide | Operational | NA | Initiate Emergency Service Patrol Program | During Evacuation | 4000 | Daily
6 | 63 | Capacity | CR 520 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 70000
6 | 64 | Capacity | CR 520 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 230000
6 | 65 | Capacity | CR 520 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0
6 | 66 | Capacity | CR 520 | Rumson Bridge | Physical | Œ | Widen Bridge to 42 feet | Intermediate | 500000
6 | 67 | Capacity | CR 520 | Rumson Bridge | System Management | Œ | Coordinate evacuation planning initiatives with NJTPA activities associated with the Rumson Rd. over Shrewsbury River Study | Short | 0
6 | 68 | Capacity | CR 520 | Pinckney Road | Physical |  | Add "No Parking During Evacuation" Placards | Short | 6000
6 | 69 | Capacity | CR 520 | Pinckney Road | Operational |  | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
6 | 70 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Physical | Ž | Major capital improvement connecting Rumson Rd. and Newman Springs Rd. | Long | 30000000
6 | 71 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | System Management | Ž | Coordinate road enhancement program in the vicinity of the Broad Street / SR 35 Intersection. | Intermediate | 0
6 | 72 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Detour Rumson Rd. WB traffic to White Rd. and SR 35 NB to access Newman Springs Rd. and provide "Alt" Signing | During Evacuation | 2000
6 | 73 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Upgrade White Rd., as necessary to function as a portal section and install Coastal Evacuation route signs | Long | 1900000
6 | 74 | Capacity | CR 520 | NJ GSP Exit 109 SB entrance ramp | Physical |  | Construct cross-over ramp section that would connect GSP SB entrance ramp to the GSP SB exit ramp; reverse direction of exit ramp from SB to NB | Intermediate | 198000
6 | 75 | Capacity | CR 520 | NJ GSP Exit 109 SB entrance ramp | Operational |  | Close ramp, provide police enforcement | During Evacuation | 5000 | Daily
6 | 76 | Capacity | CR 520 | NJ GSP Exit 109 | System Management |  | Coordinate GSP ramp reversal activities with NJOEM and NJDOT | Short | 0
7 | 77 | Capacity | SR 36 (Central) | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 14000000
7 | 78 | Capacity | SR 36 (Central) | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 5000
7 | 79 | Capacity | SR 36 (Central) | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
7 | 80 | Capacity | SR 36 (Central) | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 4000 | Daily
7 | 81 | Capacity | SR 36 (Central) | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 98000
7 | 82 | Capacity | SR 36 (Central) | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 322000
7 | 83 | Capacity | SR 36 (Central) | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0
7 | 84 | Capacity | SR 36 (Central) | SR 36 between Clifton Ave. and Washington Street | Physical | Œ | RE-stripe to provide one additional WB lane | Short | 30000
7 | 85 | Capacity | SR 36 (Central) | SR 36/Florence Ave. unsignalized intersection | Operational |  | Deploy police resources | During Evacuation | 500 | Daily
7 | 86 | Capacity | SR 36 (Central) | Florence Ave. between MacArthur Ave. and SR 36 | Operational |  | Close Florence Close Florence Ave. SB between MacArthur Way and SR 36 (option to deploying police as above) | During Evacuation | 0
7 | 87 | Capacity | SR 36 (Central) | Bridge over Troutmans Creek | Physical | Ž | Option - Widen Bridge to 42 feet and provide one travel lane and full hard running shoulder in each direction | Long | 44000
7 | 88 | Capacity | SR 36 (Central) | SR 36 connections at Clifton Ave., Long Branch Ave., Liberty St., Rockwell Ave., Seventh Ave., Washington St. | Operational |  | Prohibit left-turn in WB direction; deploy police at each intersection. | During Evacuation | 3000 | Daily
7 | 89 | Capacity | SR 36 (Central) | At-grade RR crossing near Washington St. | System Management |  | Coordinate portal improvements near RR crossing with NJ Transit | Long | 0
7 | 90 | Flooding | SR 36 (Central) | (MP 4.4 to MP5.5 - Long Branch Ave.) | System Management |  | Coordinate this future candidate drainage project with NJ Transit | Long | 0
7 | 91 | Capacity | SR 36 (Central) | SR 36 between Branchport Ave. and Victor Ave. | Operational |  | Create two temporary WB lanes using traffic control devices and deployment of police. | During Evacuation | 1000
7 | 92 | Capacity | SR 36 (Central) | SR 36 between Washington St. and Victor Ave. | Operational | ‘ | Narrow grassy median, install third WB travel lane | Long | 5000000
7 | 93 | Capacity | SR 36 (Central) | NJ GSP Exit105 | Operational | ’ | Reverse direction and function of GSP Exit ramp to SR 36 EB; make it an on-ramp to GSP and change its direction from SB to NB | Short | 5000 | Daily
8 | 94 | Capacity | Park Ave. | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 3300000
8 | 95 | Capacity | Park Ave. | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2400
8 | 96 | Capacity | Park Ave. | Corridor Wide | Physical | NA | Install Coastal Evacuation Route signing throughout route | Short | 8000
8 | 97 | Capacity | Park Ave. | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
8 | 98 | Capacity | Park Ave. | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000
8 | 99 | Capacity | Park Ave. | Corridor Wide | Operational | NA | Coordinate Highway Advisory Radio Messages through nearby systems | Short | 0
8 | 100 | Capacity | Park Ave. | Corridor Wide | System Management | NA | Where appropriate, coordinate corridor improvments with NJTPA 2030 Plan intiatives | Long | 0
8 | 101 | Capacity | Park Ave. | Corridor Wide | System Management | NA | Provide evacuees with emergency information through a public communication program | Short | 0
8 | 102 | Capacity | Park Ave. | NJ Coast Line Crossing, West of Lincoln Ave. | System Management | Œ | Coordinate improvements with NJ Transit to account for Evacuation | Long | 0
8 | 103 | Capacity | Park Ave. | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Technological | Ž | Provide Portable Traffic Signals | Intermediate | 60000
8 | 104 | Capacity | Park Ave. | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Operational | Ž | Provide police enforcement | During Evacuation | 4000 | Daily
8 | 105 | Capacity | Park Ave. | Corridor Wide | Technological | Ž | LED and Backup Power for Signals | Intermediate | 35000
8 | 106 | Capacity | Park Ave. | Corridor Wide | Technological | Ž | Upgrade signals for wireless control | Intermediate | 115000
9 | 107 | Capacity | CR 16 | Corridor Wide | Physical | NA | Widen to create full shoulder | Long | 9000000
9 | 108 | Capacity | CR 16 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3400
9 | 109 | Capacity | CR 16 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Daily
9 | 110 | Capacity | CR 16 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
9 | 111 | Capacity | CR 16 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 105000
9 | 112 | Capacity | CR 16 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 345000
9 | 113 | Capacity | CR 16 | Corridor Wide | System Management | NA | Provide Highway Advisory Radio for this and other nearby corridors | Intermediate | 35000
9 | 114 | Capacity | CR 16 | Seaview Sq. Mall entrances to CR 16 | Operational | Œ | Allow only one exit ramp from the mall onto CR 16 | During Evacuation | 5000 | Daily
9 | 115 | Capacity | CR 16 | Wayside Rd. to Jumping Brook Rd. | Physical |  | Widen State Route 66 | Long | 3800000
9 | 116 | Capacity | CR 16 | Asbury Park between Essex Rd. and Green Grove Rd. | Operational | Ž | Close business driveways located on south side of Asbury Ave. Provide police enforcement | During Evacuation | 2000 | Daily
9 | 117 | Capacity | CR 16 | Asbury Ave./Essex Rd. unsignalized intersection | Technological |  | Provide Portable Traffic Signals | Intermediate | 60000
9 | 118 | Capacity | CR 16 | Asbury Ave./Essex Rd. unsignalized intersection | Operational |  | Provide police enforcement | During Evacuation | 2000 | Daily
9 | 119 | Capacity | CR 16 | NJ GSP Exit 102 | Operational |  | Close GSP entrance ramp and reverse direction of GSP exit ramp; provide police enforcement | During Evacuation | 2000 | Daily
9 | 120 | Capacity | CR 16 | CR 16/Foxchase Drive unsignalized intersection | Operational | ‘ | Provide police enforcement | During Evacuation | 2000 | Daily
9 | 121 | Capacity | CR 16 | CR 16/CR 547 intersection | Physical | ’ | Widen CR 16 westbound approach to provide full shoulder; also widen intersection's west leg to provide two departure lanes | Long | 500000
10 | 122 | Capacity | SR 33 | Corridor Wide | Physical | NA | Widen to create full shoulder | Long | 10000000
10 | 123 | Capacity | SR 33 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3700
10 | 124 | Capacity | SR 33 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuations | 2000 | Daily
10 | 125 | Capacity | SR 33 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuations | 5000 | Daily
10 | 126 | Capacity | SR 33 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 105000
10 | 127 | Capacity | SR 33 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 345000
10 | 128 | Capacity | SR 33 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0
10 | 129 | Capacity | SR 33 | Corridor Wide | System Management | NA | Institute public communication program through multi-media sources to provide evacuees with information about emergency shelters | During Evacuation | 0
10 | 130 | Capacity | SR 33 | Corridor Wide | Physical | NA | Promote coordination with the new HAR proposed for Neptune in this report. | Intermediate | 0
10 | 131 | Capacity | SR 33 | SR 33 WB between Atkins Ave. and Myrtle Ave. | Physical | Œ | Provide second westbound lane thorugh a combination of pavement re-striping, narrowing center median, and realigning sidewalk | Long | 250000
10 | 132 | Capacity | SR 33 | SR 33 at NJ GSP Exit 100A | Physical |  | Construct crossover between GSP on-ramp and exit ramp | Long | 750000
10 | 133 | Capacity | SR 33 | SR 33 at NJ GSP Exit 100A | Operational |  | Provide police enforcement | During Evacuation | 4000 | Daily
11 | 134 | Capacity | CR 524 (Allaire) | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 7700000
11 | 135 | Capacity | CR 524 (Allaire) | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3000
11 | 136 | Capacity | CR 524 (Allaire) | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Daily
11 | 137 | Capacity | CR 524 (Allaire) | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Daily
11 | 138 | Capacity | CR 524 (Allaire) | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | LED and Backup Power for Signals | Intermediate | 21000
11 | 139 | Capacity | CR 524 (Allaire) | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | Upgrade signals for wireless control | Intermediate | 69000
11 | 140 | Capacity | CR 524 (Allaire) | SR 34, between Traffic Circle and Allenwood Rd. | Physical | Ž | Install third travel lane in northbound direction between traffic circle and Allenwood Rd. | Long | 1100000
11 | 141 | Capacity | CR 524 (Allaire) | SR 34 Traffic Circle | Physical |  | Convert traffic circle into signalized intersection | Long | 10000000
11 | 142 | Capacity | CR 524 (Allaire) | Cr 524/Allenwood Rd./Ridgewood Rd. | Operational |  | Control traffic flow using police | During Evacuation | 500 | Daily
11 | 143 | Capacity | CR 524 (Allaire) | Cr 524/Allenwood Rd./Ridgewood Rd. | Technological |  | Install flashing beacons to control traffic flow through intersection | Short | 10000
12 | 144 | Capacity | CR 524 Spur | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 8800000
12 | 145 | Capacity | CR 524 Spur | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3200
12 | 146 | Capacity | CR 524 Spur | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | na
12 | 147 | Capacity | CR 524 Spur | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Daily
12 | 148 | Capacity | CR 524 Spur | CR 20 (Broad Street) | Technological | Œ | LED and Backup Power for Signals | Intermediate | 7000
12 | 149 | Capacity | CR 524 Spur | CR 20 (Broad Street) | Technological | Œ | Upgrade signals for wireless control | Intermediate | 23000
12 | 150 | Capacity | CR 524 Spur | SR 35/CR 524 Spur Traffic Circle | Physical |  | Eliminate traffic circle | Long | 10000000
12 | 151 | Capacity | CR 524 Spur | Tilton Corner Road | Operational | Ž | Close road and detour traffic to Ridgewood Road | During Evacuation | 4000 | Daily
12 | 152 | Capacity | CR 524 Spur | CR 524 Spur at Ramshorn Drive | Operational |  | Deploy police at unsignalized intersection | During Evacuation | 500 | Daily
[6 empty] |  | 140

## Treatments
Issue | Portal Route | Location | Treatment Category | Treatment | Timeframe | Estimated Cost 1 | Unit
Capacity | County Route 39 | Corridor Wide | Operational | Restriping | Short | 5 | roadway-ft
Capacity |  |  | Operational | Enforce "No Parking During Evacuations" | During Emergency | 2000 | na
Capacity |  |  | Operational | Emergency Service Patrols | During Emergency | 5000
Flooding |  |  | Operational | Police Assist | During Emergency | 500 | Officer/Day
Capacity |  |  | Physical | Minor Widening <3 feet | Intermediate | 150000 | MILE
Capacity |  |  | Physical | New Bridge | Long | 220 | Sq Foot
Capacity |  |  | Physical | Rehabilitate Bridge | Long | 150 | Sq Foot
Capacity |  |  | Physical | Relocate Aerial Utilities | Long | 100000 | MILE
Capacity |  |  | Physical | Reverse On-Ramp | Long | 500000 | Location
Capacity |  |  | Physical | Widening - add lane | Long | 2100000 | Lane-Mile
Flooding |  |  | Physical | Raise Roadway - 1 foot | Long | 720 | Lane- foot
Flooding |  |  | Physical | MODIFY SIGN | Short | 600 | MILE
Flooding |  |  | Physical | New Signs | Short | 1500 | MILE
Capacity |  |  | Physical | Emergency Shelters | Short | 0 | #N/A
Flooding |  |  | System Management | Plan to focus on Intense Inundation Areas | During Emergency | 0 | #N/A
Capacity |  |  | System Management | Add "No Parking During Evacuation" Placards | Short | 0 | na
Capacity |  |  | System Management | Install Coastal Evacuation Route signing throughout route | Short | 2000 | na
Capacity |  |  | Technological | HAR: Transmitter, two signs | Intermediate | 35000 | Area
Capacity |  |  | Technological | LED and Backup Power for Signals | Intermediate | 7000 | Location
Capacity |  |  | Technological | Upgrade signals for wireless control | Intermediate | 23000 | Location
Capacity |  |  | Technological | (Permanent) Dynamic Message Signs | Intermediate | 25000 | Location
Capacity |  |  | Technological | Portable Traffic Signals | Intermediate | 60000 | Location
Notes:
1 | Costs do not include Right-of-Way costs
2 | "During Emergency" costs are estimated as per-day
3 | Bridge Reconstruction was recently completed

## EVACDB3
RouteNO | ORDER KEY | Issue | Portal Route | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment | LOCATION 1 LATITUDE | LOCATION 1 LONGITUDE | LOCATION 2 LATITUDE | LOCATION 2 LONGITUDE | LOCATION 3 LATITUDE | LOCATION 3 LONGITUDE | LOCATION 4 LATITUDE | LOCATION 4 LONGITUDE | LOCATION 5 LATITUDE | LOCATION 5 LONGITUDE
1 | 10 | Capacity | County Route 39 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2400 | County
1 | 20 | Capacity | County Route 39 | Corridor Wide | Physical | NA | Widen to 42 feet | Long | 400000 | County
1 | 30 | Capacity | County Route 39 | Corridor Wide | Physical | NA | Install Coastal Evacuation Route Signs | Short | 1500 | County
1 | 40 | Capacity | County Route 39 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2300 | Municipality | Daily
1 | 50 | Capacity | County Route 39 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
1 | 60 | Flooding | County Route 39 | Flat Creek Bridge | Physical | Œ | New Bridge | Short | 0 | N/A | Project is Completed | 40° 26' 50.37" | 74° 09' 59.94"
1 | 70 | Flooding | County Route 39 | East Creek | Physical | Ž | Elevate Roadway, Improve Drainage | Long | 10000000 | State |  | 40° 26' 17.86" | 74° 09' 53.03"
1 | 80 | Capacity | County Route 39 | Washington Avenue to SR 36 | Physical |  | Hard Running Shoulder | Intermediate | 50000 | State/County |  | 40° 26' 17.26" | 74° 09' 44.11"
1 | 90 | Capacity | County Route 39 | Washington Avenue to SR 36 | Physical |  | Relocate Utilities | Intermediate | 35000 | State/County |  | 40° 26' 17.26" | 74° 09' 44.11"
1 | 100 | Capacity | County Route 39 | Hemlock Street | Operational |  | Two-phase signal during evacuations. Divert NB Traffic. | During Evacuations | 4000 | County/Local | Daily | 40° 26' 11.28" | 74° 09' 51.74"
1 | 110 | Flooding | County Route 39 | SR 36/Union Ave | Technological |  | LED and Backup Power for Signals | Intermediate | 7000 | State/County | location | 40° 26' 16.81" | 74° 09' 52.38"
1 | 120 | Flooding | County Route 39 | SR 36/Union Ave | Technological |  | Upgrade signals for wireless control | Intermediate | 23000 | State/County | location | 40° 26' 16.81" | 74° 09' 52.38"
2 | 130 | Capacity | CR 56/CR 7 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 1400 | County/MCOEM
2 | 140 | Capacity | CR 56/CR 7 | Corridor Wide | Physical | NA | Install Coastal Evacuation Route Signing at Critical Intersections | Short | 2000 | County/MCOEM
2 | 150 | Capacity | CR 56/CR 7 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality
2 | 160 | Capacity | CR 56/CR 7 | Corridor Wide | Operational | NA | Coordinate Existing Highway Advisory System | Short | 0 | State/County OEM
2 | 170 | Flooding | CR 56/CR 7 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
2 | 180 | Capacity | CR 56/CR 7 | Carr Ave | Operational | Œ | Close Circuit Street | During Evacuation | 1000 | Municipality | Daily | 40° 26' 52.75" | 74° 08' 00.45"
2 | 190 | Capacity | CR 56/CR 7 | Carr Ave | Physical |  | Re-stripe | Short | 27000 | County |  | 40° 26' 34.49" | 74° 07' 55.28"
2 | 200 | Capacity | CR 56/CR 7 | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | LED and Backup Power for Signals | Intermediate | 21000 | State/County | Location | 40° 26' 30.36" | 74° 07' 53.41" | 40° 26' 07.52" | 74° 07' 52.61" | 40° 26' 48.29" | 74° 07' 26.71"
2 | 210 | Capacity | CR 56/CR 7 | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | Upgrade signals for wireless control | Intermediate | 69000 | State/County | Location | 40° 26' 07.52" | 74° 07' 53.41" | 40° 26' 07.52" | 74° 07' 52.61" | 40° 26' 48.29" | 74° 07' 26.71"
2 | 220 | Capacity | CR 56/CR 7 | Church St. | Operational |  | Use parking lane as a through street - Police | During Evacuation | 500 | Municipality | Daily | 40° 26' 30.51" | 74° 07' 51.60"
2 | 230 | Capacity | CR 56/CR 7 | Main St./Henry Hudson Bike Trail | Operational |  | Control Crossing Using Police | During Evacuation | 500 | Municipality | Daily | 40° 26' 24.81" | 74° 07' 48.73"
2 | 240 | Capacity | CR 56/CR 7 | Main St./SR 36 | Physical | ‘ | Widen to create full shoulder | Intermediate | 300000 | State |  | 40° 26' 22.25" | 74° 07' 49.36"
2 | 250 | Capacity | CR 56/CR 7 | Main St./SR 36 | Operational | ‘ | Control Crossing Using Police | During Evacuation | 500 | Municipality | Daily | 40° 26' 22.25" | 74° 07' 49.36"
3 | 260 | Capacity | SR 36 (N) | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 30000000 | State
3 | 270 | Capacity | SR 36 (N) | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 10400 | County with State Approval
3 | 280 | Capacity | SR 36 (N) | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
3 | 290 | Capacity | SR 36 (N) | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
3 | 300 | Capacity | SR 36 (N) | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 154000 | State
3 | 310 | Capacity | SR 36 (N) | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 506000 | State
3 | 320 | Capacity | SR 36 (N) | Corridor Wide | Operational | NA | Coordinate Existing Highway Advisory System | Short | 0 | Municipalities with MCOEM
3 | 330 | Capacity | SR 36 (N) | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
3 | 340 | Capacity | SR 36 (N) | Highlands/Sea Bright | Physical | Œ | New Bridge | Under Construction | 0 | State |  | 40° 23' 46.56" | 73° 58' 45.63"
3 | 350 | Capacity | SR 36 (N) | CR8A | Physical |  | Install Dynamic Message Sign | Intermediate | 30000 | State |  | 40° 24' 09.93" | 73° 59' 45.65"
3 | 360 | Capacity | SR 36 (N) | CR 8A | Physical | Ž | Reconfigure Intersection | Long | 170000 | State/County |  | 40° 24' 18.92" | 74° 00' 17.68"
3 | 370 | Capacity | SR 36 (N) | Normandy Road Underpass | Physical | ‘ | Create one-lane bypass under bridge | Intermediate | 600000 | State |  | 40° 24' 59.86" | 74° 04' 12.88"
3 | 380 | Capacity | SR 36 (N) | Broad Street | Physical | ’ | Widen at Intersection | Intermediate | 4000000 | State/County |  | 40° 25' 37.15" | 74° 11' 48.20"
3 | 390 | Flooding | SR 36 (N) | Lupatatong Creek | Physical |  | Elevate Roadway, Improve Drainage | Long | 6500000 | State/County |  | 40° 24' 37.02" | 74° 02' 35.48"
3 | 400 | Flooding | SR 36 (N) | Many Mind / Wagner Creek | Physical |  | Elevate Roadway, Improve Drainage | Intermediate | 6500000 | State |  | 40° 24' 47.86" | 74° 03' 07.39"
4 | 410 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 6000000 | County | Not including Harmony Road (below)
4 | 420 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2100 | County
4 | 430 | Capacity | CR 516/ CR 50 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
4 | 440 | Capacity | CR 516/ CR 50 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
4 | 450 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | NA | Add Evacuation Route signing at key locations | Short | 1600 | County
4 | 460 | Capacity | CR 516/ CR 50 | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | LED and Backup Power for Signals | Intermediate | 28000 | County |  | 40° 24' 52.53" | 74° 05' 13.89" | 40° 24' 53.09" | 74° 05' 40.95" | 40° 24' 42.94" | 74° 06' 10.49"
4 | 470 | Capacity | CR 516/ CR 50 | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | Upgrade signals for wireless control | Intermediate | 92000 | County |  | 40° 24' 52.53" | 74° 05' 13.89" | 40° 24' 53.09" | 74° 05' 40.95" | 40° 24' 42.94" | 74° 06' 10.49"
4 | 480 | Capacity | CR 516/ CR 50 | Church Street | Operational |  | Close a portion of Church Street in the SB Direction, Install temporary detour signs | During Evacuation | 2000 | Municipality |  | 40° 24' 45.86" | 74° 06' 04.75"
4 | 490 | Capacity | CR 516/ CR 50 | SR 35 / CR 50 | Physical |  | Widen roadbed between CR 50 and Harmony Road | Long | 1500000 | State/County |  | 40° 23' 46.56" | 74° 06' 47.03"
4 | 500 | Capacity | CR 516/ CR 50 | Parking Lot, SR 36 | Operational | Ž | Close southerly driveway entrance | During Evacuation | 500 | Municipality |  | 40° 23' 56.64" | 74° 06' 48.58"
5 | 510 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 12500000 | County
5 | 520 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Physical | NA | Install Coastal Evacuation Route signing throughout route | Short | 4500 | County
5 | 530 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality
5 | 540 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality
5 | 550 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 42000 | County
5 | 560 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 138000 | County
5 | 570 | Flooding | CR 8A / 12A / 12 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
5 | 580 | Capacity | CR 8A / 12A / 12 | Oceanic Bridge | Physical | Œ | Reconstruct Bridge | Long | 50000000 | County/State/ Federal |  | 40° 22' 52.73" | 74° 00' 50.46"
5 | 590 | Capacity | CR 8A / 12A / 12 | NJ GSP Exit 114 | Operational |  | Close connecting ramp between GSP on-and off ramps; reverse GSP southbound Exit Ramp to Red Hill Rd. | During Evacuation | 8000 | Municipality | Daily | 40° 22' 25.29" | 74° 08' 53.57"
5 | 600 | Capacity | CR 8A / 12A / 12 | NJ GSP Exit 114 | System Management | Ž | Coordinate GSP ramp reversal activities with NJMCOEM and NJDOT | Short | 0 | MCOEM |  | 40° 22' 25.29" | 74° 08' 53.57"
6 | 610 | Capacity | CR 520 | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 16500000 | County
6 | 620 | Capacity | CR 520 | Corridor Wide | Operational | NA | Initiate Emergency Service Patrol Program | During Evacuation | 4000 | Municipality | Daily
6 | 630 | Capacity | CR 520 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 70000 | Municipality
6 | 640 | Capacity | CR 520 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 230000 | County
6 | 650 | Capacity | CR 520 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
6 | 660 | Capacity | CR 520 | Rumson Bridge | Physical | Œ | Widen Bridge to 42 feet | Intermediate | 500000 | County |  | 40° 21' 56.89" | 73° 58' 31.94"
6 | 670 | Capacity | CR 520 | Rumson Bridge | System Management | Œ | Coordinate evacuation planning initiatives with NJTPA activities associated with the Rumson Rd. over Shrewsbury River Study | Short | 0 | MCOEM |  | 40° 21' 56.89" | 73° 58' 31.94"
6 | 680 | Capacity | CR 520 | Pinckney Road | Physical |  | Add "No Parking During Evacuation" Placards | Short | 6000 | County |  | 40° 20' 26.81" | 74° 03' 24.09"
6 | 690 | Capacity | CR 520 | Pinckney Road | Operational |  | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily | 40° 20' 26.81" | 74° 03' 24.09"
6 | 700 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Physical | Ž | Major capital improvement connecting Rumson Rd. and Newman Springs Rd. | Long | 30000000 | County / Municipality / State |  | 40° 20' 14.98" | 74° 02' 56.15" | 40° 20' 17.47" | 74° 03' 49.35" | 40° 20' 09.27" | 74° 03' 16.55"
6 | 710 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | System Management | Ž | Coordinate road enhancement program in the vicinity of the Broad Street / SR 35 Intersection. | Intermediate | 0 | County / NJTPA/ State |  | 40° 20' 14.98" | 74° 02' 56.15" | 40° 20' 17.47" | 74° 03' 49.35" | 40° 20' 09.27" | 74° 03' 16.55"
6 | 720 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Detour Rumson Rd. WB traffic to White Rd. and SR 35 NB to access Newman Springs Rd. and provide "Alt" Signing | During Evacuation | 2000 | Municipality |  | 40° 20' 14.98" | 74° 02' 56.15" | 40° 20' 17.47" | 74° 03' 49.35" | 40° 20' 09.27" | 74° 03' 16.55"
6 | 730 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Upgrade White Rd., as necessary to function as a portal section and install Coastal Evacuation route signs | Long | 1900000 | Municipality |  | 40° 20' 14.98" | 74° 02' 56.15" | 40° 20' 17.47" | 74° 03' 49.35" | 40° 20' 09.27" | 74° 03' 16.55"
6 | 740 | Capacity | CR 520 | NJ GSP Exit 109 SB entrance ramp | Physical |  | Construct cross-over ramp section that would connect GSP SB entrance ramp to the GSP SB exit ramp; reverse direction of exit ramp from SB to NB | Intermediate | 198000 | State |  | 40° 20' 11.44" | 74° 06' 09.24"
6 | 750 | Capacity | CR 520 | NJ GSP Exit 109 SB entrance ramp | Operational |  | Close ramp, provide police enforcement | During Evacuation | 5000 | State | Daily | 40° 20' 11.44" | 74° 06' 09.24"
6 | 760 | Capacity | CR 520 | NJ GSP Exit 109 | System Management |  | Coordinate GSP ramp reversal activities with NJMCOEM and NJDOT | Short | 0 | State/ MCOEM |  | 40° 20' 11.44" | 74° 06' 09.24"
7 | 770 | Capacity | SR 36 (Central) | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 14000000 | State
7 | 780 | Capacity | SR 36 (Central) | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 5000 | County with State Approval
7 | 790 | Capacity | SR 36 (Central) | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
7 | 800 | Capacity | SR 36 (Central) | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 4000 | Municipality | Daily
7 | 810 | Capacity | SR 36 (Central) | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 98000 | State
7 | 820 | Capacity | SR 36 (Central) | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 322000 | State
7 | 830 | Capacity | SR 36 (Central) | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
7 | 840 | Capacity | SR 36 (Central) | SR 36 between Clifton Ave. and Washington Street | Physical | Œ | RE-stripe to provide one additional WB lane | Short | 30000 | State |  | 40° 18' 48.28" | 73° 58' 51.55"
7 | 850 | Capacity | SR 36 (Central) | SR 36/Florence Ave. unsignalized intersection | Operational |  | Deploy police resources | During Evacuation | 500 | Municipality | Daily | 40° 18' 47.64" | 73° 59' 09.29"
7 | 860 | Capacity | SR 36 (Central) | Florence Ave. between MacArthur Ave. and SR 36 | Operational |  | Close Florence Close Florence Ave. SB between MacArthur Way and SR 36 (option to deploying police as above) | During Evacuation | 0 | Municipality |  | 40° 18' 47.64" | 73° 59' 09.29"
7 | 870 | Capacity | SR 36 (Central) | Bridge over Troutmans Creek | Physical | Ž | Option - Widen Bridge to 42 feet and provide one travel lane and full hard running shoulder in each direction | Long | 44000 | State |  | 40° 18' 45.06" | 73° 59' 12.44"
7 | 880 | Capacity | SR 36 (Central) | SR 36 connections at Clifton Ave., Long Branch Ave., Liberty St., Rockwell Ave., Seventh Ave., Washington St. | Operational |  | Prohibit left-turn in WB direction; deploy police at each intersection. | During Evacuation | 3000 | Municipality | Daily | 40° 18' 21.73" | 74° 00' 14.72" | 40° 18' 25.14" | 74° 00' 05.67"
7 | 890 | Capacity | SR 36 (Central) | At-grade RR crossing near Washington St. | System Management |  | Coordinate portal improvements near RR crossing with NJ Transit | Long | 0 | NJ TRANSIT / MCOEM |  | 40° 18' 25.14" | 74° 00' 05.67" | 40° 17' 26.89" | 74° 04' 12.96"
7 | 900 | Flooding | SR 36 (Central) | (MP 4.4 to MP5.5 - Long Branch Ave.) | System Management |  | Coordinate this future candidate drainage project with NJ Transit | Long | 0 | STATE / COUNTY/ NJ TRANSIT |  | 40° 18' 25.14" | 74° 00' 05.67" | 40° 17' 26.89" | 74° 04' 12.96"
7 | 910 | Capacity | SR 36 (Central) | SR 36 between Branchport Ave. and Victor Ave. | Operational |  | Create two temporary WB lanes using traffic control devices and deployment of police. | During Evacuation | 1000 | MCOEM/ Municipality |  | 40° 18' 21.73" | 74° 00' 14.72" | 40° 18' 25.14" | 74° 00' 05.67" | 40° 17' 26.89" | 74° 04' 12.96"
7 | 920 | Capacity | SR 36 (Central) | SR 36 between Washington St. and Victor Ave. | Operational | ‘ | Narrow grassy median, install third WB travel lane | Long | 5000000 | State |  | 40° 17' 26.89" | 74° 04' 12.96"
7 | 930 | Capacity | SR 36 (Central) | NJ GSP Exit105 | Operational | ’ | Reverse direction and function of GSP Exit ramp to SR 36 EB; make it an on-ramp to GSP and change its direction from SB to NB | Short | 5000 | State | Daily | 40° 17' 26.89" | 74° 04' 12.96"
8 | 940 | Capacity | Park Ave. | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 3300000 | County
8 | 950 | Capacity | Park Ave. | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2400 | County
8 | 960 | Capacity | Park Ave. | Corridor Wide | Physical | NA | Install Coastal Evacuation Route signing throughout route | Short | 8000 | County
8 | 970 | Capacity | Park Ave. | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
8 | 980 | Capacity | Park Ave. | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality
8 | 990 | Capacity | Park Ave. | Corridor Wide | Operational | NA | Coordinate Highway Advisory Radio Messages through nearby systems | Short | 0 | MCOEM/ Municipality
8 | 1000 | Capacity | Park Ave. | Corridor Wide | System Management | NA | Where appropriate, coordinate corridor improvements with NJTPA 2030 Plan initiatives | Long | 0 | State/ County/ NJTPA
8 | 1010 | Capacity | Park Ave. | Corridor Wide | System Management | NA | Provide evacuees with emergency information through a public communication program | Short | 0 | MCOEM
8 | 1020 | Capacity | Park Ave. | NJ Coast Line Crossing, West of Lincoln Ave. | System Management | Œ | Coordinate improvements with NJ Transit to account for Evacuation | Long | 0 | County/ NJ Transit |  | 40° 16' 11.64" | 73° 59' 43.70"
8 | 1030 | Capacity | Park Ave. | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Technological |  | Provide Portable Traffic Signals | Intermediate | 60000 | County/ Municipality |  | 40° 16' 15.41" | 74° 00' 56.89" | 40° 16' 10.21" | 74° 00' 55.38"
8 | 1040 | Capacity | Park Ave. | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Operational |  | Provide police enforcement | During Evacuation | 4000 | Municipality | Daily | 40° 16' 15.41" | 74° 00' 56.89" | 40° 16' 10.21" | 74° 00' 55.38"
8 | 1050 | Capacity | Park Ave. | Corridor Wide | Technological |  | LED and Backup Power for Signals | Intermediate | 35000 | County |  | 40° 16' 15.41" | 74° 00' 56.89" | 40° 16' 10.21" | 74° 00' 55.38"
8 | 1060 | Capacity | Park Ave. | Corridor Wide | Technological |  | Upgrade signals for wireless control | Intermediate | 115000 | County |  | 40° 16' 15.41" | 74° 00' 56.89" | 40° 16' 10.21" | 74° 00' 55.38"
9 | 1070 | Capacity | CR 16 | Corridor Wide | Physical | NA | Widen to create full shoulder | Long | 9000000 | County
9 | 1080 | Capacity | CR 16 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3400 | County
9 | 1090 | Capacity | CR 16 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
9 | 1100 | Capacity | CR 16 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
9 | 1110 | Capacity | CR 16 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 105000 | County/ State
9 | 1120 | Capacity | CR 16 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 345000 | County/ State
9 | 1130 | Capacity | CR 16 | Corridor Wide | System Management | NA | Provide Highway Advisory Radio for this and other nearby corridors | Intermediate | 35000 | MCOEM
9 | 1140 | Capacity | CR 16 | Seaview Sq. Mall entrances to CR 16 | Operational | Œ | Allow only one exit ramp from the mall onto CR 16 | During Evacuation | 5000 | Municipality | Daily | 40° 13' 40.55" | 74° 02' 44.00"
9 | 1150 | Capacity | CR 16 | Wayside Rd. to Jumping Brook Rd. | Physical |  | Widen State Route 66 | Long | 3800000 | State |  | 40° 13' 46.41" | 74° 03' 47.88"
9 | 1160 | Capacity | CR 16 | Asbury Park between Essex Rd. and Green Grove Rd. | Operational | Ž | Close business driveways located on south side of Asbury Ave. Provide police enforcement | During Evacuation | 2000 | Municipality | Daily | 40° 14' 03.96" | 74° 04' 38.76"
9 | 1170 | Capacity | CR 16 | Asbury Ave./Essex Rd. unsignalized intersection | Technological |  | Provide Portable Traffic Signals | Intermediate | 60000 | MCOEM/ Municipality |  | 40° 14' 12.01" | 74° 04' 54.03"
9 | 1180 | Capacity | CR 16 | Asbury Ave./Essex Rd. unsignalized intersection | Operational |  | Provide police enforcement | During Evacuation | 2000 | Municipality | Daily | 40° 14' 12.01" | 74° 04' 54.03"
9 | 1190 | Capacity | CR 16 | NJ GSP Exit 102 | Operational |  | Close GSP entrance ramp and reverse direction of GSP exit ramp; provide police enforcement | During Evacuation | 2000 | State | Daily | 40° 40' 14.26" | 74° 05' 24.89"
9 | 1200 | Capacity | CR 16 | CR 16/Foxchase Drive unsignalized intersection | Operational | ‘ | Provide police enforcement | During Evacuation | 2000 | Municipality | Daily | 40° 40' 14.37" | 74° 05' 38.91"
9 | 1210 | Capacity | CR 16 | CR 16/CR 547 intersection | Physical | ’ | Widen CR 16 westbound approach to provide full shoulder; also widen intersection's west leg to provide two departure lanes | Long | 500000 | County |  | 40° 40' 49.20" | 74° 06' 01.72"
10 | 1220 | Capacity | SR 33 | Corridor Wide | Physical | NA | Widen to create full shoulder | Long | 10000000 | State
10 | 1230 | Capacity | SR 33 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3700 | County with State Approval
10 | 1240 | Capacity | SR 33 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuations | 2000 | Municipality | Daily
10 | 1250 | Capacity | SR 33 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuations | 5000 | Municipality | Daily
10 | 1260 | Capacity | SR 33 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 105000 | State
10 | 1270 | Capacity | SR 33 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 345000 | State
10 | 1280 | Capacity | SR 33 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
10 | 1290 | Capacity | SR 33 | Corridor Wide | System Management | NA | Institute public communication program through multi-media sources to provide evacuees with information about emergency shelters | During Evacuation | 0 | MCOEM
10 | 1300 | Capacity | SR 33 | Corridor Wide | Physical | NA | Promote coordination with the new HAR proposed for Neptune in this report. | Intermediate | 0 | MCOEM
10 | 1310 | Capacity | SR 33 | SR 33 WB between Atkins Ave. and Myrtle Ave. | Physical | Œ | Provide second westbound lane thorugh a combination of pavement re-striping, narrowing center median, and realigning sidewalk | Long | 250000 | State |  | 40° 12' 36.52" | 74° 01' 17.50"
10 | 1320 | Capacity | SR 33 | SR 33 at NJ GSP Exit 100A | Physical |  | Construct crossover between GSP on-ramp and exit ramp | Long | 750000 | State
10 | 1330 | Capacity | SR 33 | SR 33 at NJ GSP Exit 100A | Operational | Ž | Provide police enforcement | During Evacuation | 4000 | Municipality | Daily
11 | 1340 | Capacity | CR 524 (Allaire) | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 7700000 | County
11 | 1350 | Capacity | CR 524 (Allaire) | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3000 | County
11 | 1360 | Capacity | CR 524 (Allaire) | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
11 | 1370 | Capacity | CR 524 (Allaire) | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
11 | 1380 | Capacity | CR 524 (Allaire) | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | LED and Backup Power for Signals | Intermediate | 21000 | County |  | 40° 09' 15.61" | 74° 03' 17.54" | 40° 09' 13.32" | 74° 03' 30.54" | 40° 09' 08.90" | 74° 04' 21.05"
11 | 1390 | Capacity | CR 524 (Allaire) | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | Upgrade signals for wireless control | Intermediate | 69000 | State |  | 40° 09' 15.61" | 74° 03' 17.54" | 40° 09' 13.32" | 74° 03' 30.54" | 40° 09' 08.90" | 74° 04' 21.05"
11 | 1400 | Capacity | CR 524 (Allaire) | SR 34, between Traffic Circle and Allenwood Rd. | Physical | Ž | Install third travel lane in northbound direction between traffic circle and Allenwood Rd. | Long | 1100000 | State |  | 40° 09' 14.43" | 74° 05' 52.94"
11 | 1410 | Capacity | CR 524 (Allaire) | SR 34 Traffic Circle | Physical |  | Convert traffic circle into signalized intersection | Long | 10000000 | Municipality |  | 40° 09' 00.41" | 74° 05' 45.57"
11 | 1420 | Capacity | CR 524 (Allaire) | Cr 524/Allenwood Rd./Ridgewood Rd. | Operational |  | Control traffic flow using police | During Evacuation | 500 | County | Daily | 40° 08' 58.09" | 74° 06' 08.48"
11 | 1430 | Capacity | CR 524 (Allaire) | Cr 524/Allenwood Rd./Ridgewood Rd. | Technological |  | Install flashing beacons to control traffic flow through intersection | Short | 10000 | County |  | 40° 08' 58.09" | 74° 06' 08.48"
12 | 1440 | Capacity | CR 524 Spur | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 8800000 | County
12 | 1450 | Capacity | CR 524 Spur | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3200 | County
12 | 1460 | Capacity | CR 524 Spur | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | na
12 | 1470 | Capacity | CR 524 Spur | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
12 | 1480 | Capacity | CR 524 Spur | CR 20 (Broad Street) | Technological | Œ | LED and Backup Power for Signals | Intermediate | 7000 | County |  | 40° 07' 34.61" | 74° 02' 57.00"
12 | 1490 | Capacity | CR 524 Spur | CR 20 (Broad Street) | Technological | Œ | Upgrade signals for wireless control | Intermediate | 23000 | State |  | 40° 07' 34.61" | 74° 02' 57.00"
12 | 1500 | Capacity | CR 524 Spur | SR 35/CR 524 Spur Traffic Circle | Physical |  | Eliminate traffic circle | Long | 10000000 | Municipality |  | 40° 07' 56.54" | 74° 03' 54.88"
12 | 1510 | Capacity | CR 524 Spur | Tilton Corner Road | Operational | Ž | Close road and detour traffic to Ridgewood Road | During Evacuation | 4000 | Municipality | Daily | 40° 08' 27.92" | 74° 03' 05.01"
12 | 1520 | Capacity | CR 524 Spur | CR 524 Spur at Ramshorn Drive | Operational |  | Deploy police at unsignalized intersection | During Evacuation | 500 | Municipality | Daily | 40° 08' 30.78" | 74° 03' 59.60"
[6 empty] |  | 140

## EVACDB3FORGIS
RouteNO | ORDER KEY | Issue | Portal Route | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment | LOCATION 1 LATITUDE | LOCATION 1 LONGITUDE | LOCATION 2 LATITUDE | LOCATION 2 LONGITUDE | LOCATION 3 LATITUDE | LOCATION 3 LONGITUDE | LOCATION 4 LATITUDE | LOCATION 4 LONGITUDE | LOCATION 5 LATITUDE | LOCATION 5 LONGITUDE
1 | 10 | Capacity | County Route 39 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2400 | County
1 | 20 | Capacity | County Route 39 | Corridor Wide | Physical | NA | Widen to 42 feet | Long | 400000 | County
1 | 30 | Capacity | County Route 39 | Corridor Wide | Physical | NA | Install Coastal Evacuation Route Signs | Short | 1500 | County
1 | 40 | Capacity | County Route 39 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2300 | Municipality | Daily
1 | 50 | Capacity | County Route 39 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
1 | 60 | Flooding | County Route 39 | Flat Creek Bridge | Physical | Œ | New Bridge | Short | 0 | N/A | Project is Completed | 40.4473 | 74.1667
1 | 70 | Flooding | County Route 39 | East Creek | Physical | Ž | Elevate Roadway, Improve Drainage | Long | 10000000 | State |  | 40.4383 | 74.1647
1 | 80 | Capacity | County Route 39 | Washington Avenue to SR 36 | Physical |  | Hard Running Shoulder | Intermediate | 50000 | State/County |  | 40.4381 | 74.1623
1 | 90 | Capacity | County Route 39 | Washington Avenue to SR 36 | Physical |  | Relocate Utilities | Intermediate | 35000 | State/County |  | 40.4381 | 74.1623
1 | 100 | Capacity | County Route 39 | Hemlock Street | Operational |  | Two-phase signal during evacuations. Divert NB Traffic. | During Evacuations | 4000 | County/Local | Daily | 40.4365 | 74.1644
1 | 110 | Flooding | County Route 39 | SR 36/Union Ave | Technological |  | LED and Backup Power for Signals | Intermediate | 7000 | State/County | location | 40.438 | 74.1646
1 | 120 | Flooding | County Route 39 | SR 36/Union Ave | Technological |  | Upgrade signals for wireless control | Intermediate | 23000 | State/County | location | 40.438 | 74.1646
2 | 130 | Capacity | CR 56/CR 7 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 1400 | County/MCOEM
2 | 140 | Capacity | CR 56/CR 7 | Corridor Wide | Physical | NA | Install Coastal Evacuation Route Signing at Critical Intersections | Short | 2000 | County/MCOEM
2 | 150 | Capacity | CR 56/CR 7 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality
2 | 160 | Capacity | CR 56/CR 7 | Corridor Wide | Operational | NA | Coordinate Existing Highway Advisory System | Short | 0 | State/County OEM
2 | 170 | Flooding | CR 56/CR 7 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
2 | 180 | Capacity | CR 56/CR 7 | Carr Ave | Operational | Œ | Close Circuit Street | During Evacuation | 1000 | Municipality | Daily | 40.448 | 74.1335
2 | 190 | Capacity | CR 56/CR 7 | Carr Ave | Physical |  | Re-stripe | Short | 27000 | County |  | 40.4429 | 74.132
2 | 200 | Capacity | CR 56/CR 7 | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | LED and Backup Power for Signals | Intermediate | 21000 | State/County | Location | 40.4418 | 74.1315 | 40.4354 | 74.1313 | 40.4467 | 74.1241
2 | 210 | Capacity | CR 56/CR 7 | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | Upgrade signals for wireless control | Intermediate | 69000 | State/County | Location | 40.4354 | 74.1315 | 40.4354 | 74.1313 | 40.4467 | 74.1241
2 | 220 | Capacity | CR 56/CR 7 | Church St. | Operational |  | Use parking lane as a through street - Police | During Evacuation | 500 | Municipality | Daily | 40.4418 | 74.131
2 | 230 | Capacity | CR 56/CR 7 | Main St./Henry Hudson Bike Trail | Operational |  | Control Crossing Using Police | During Evacuation | 500 | Municipality | Daily | 40.4402 | 74.1302
2 | 240 | Capacity | CR 56/CR 7 | Main St./SR 36 | Physical | ‘ | Widen to create full shoulder | Intermediate | 300000 | State |  | 40.4395 | 74.1304
2 | 250 | Capacity | CR 56/CR 7 | Main St./SR 36 | Operational | ‘ | Control Crossing Using Police | During Evacuation | 500 | Municipality | Daily | 40.4395 | 74.1304
3 | 260 | Capacity | SR 36 (N) | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 30000000 | State
3 | 270 | Capacity | SR 36 (N) | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 10400 | County with State Approval
3 | 280 | Capacity | SR 36 (N) | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
3 | 290 | Capacity | SR 36 (N) | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
3 | 300 | Capacity | SR 36 (N) | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 154000 | State
3 | 310 | Capacity | SR 36 (N) | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 506000 | State
3 | 320 | Capacity | SR 36 (N) | Corridor Wide | Operational | NA | Coordinate Existing Highway Advisory System | Short | 0 | Municipalities with MCOEM
3 | 330 | Capacity | SR 36 (N) | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
3 | 340 | Capacity | SR 36 (N) | Highlands/Sea Bright | Physical | Œ | New Bridge | Under Construction | 0 | State |  | 40.3963 | 73.9793
3 | 350 | Capacity | SR 36 (N) | CR8A | Physical |  | Install Dynamic Message Sign | Intermediate | 30000 | State |  | 40.4028 | 73.996
3 | 360 | Capacity | SR 36 (N) | CR 8A | Physical | Ž | Reconfigure Intersection | Long | 170000 | State/County |  | 40.4053 | 74.0049
3 | 370 | Capacity | SR 36 (N) | Normandy Road Underpass | Physical | ‘ | Create one-lane bypass under bridge | Intermediate | 600000 | State |  | 40.4166 | 74.0702
3 | 380 | Capacity | SR 36 (N) | Broad Street | Physical | ’ | Widen at Intersection | Intermediate | 4000000 | State/County |  | 40.427 | 74.1967
3 | 390 | Flooding | SR 36 (N) | Lupatatong Creek | Physical |  | Elevate Roadway, Improve Drainage | Long | 6500000 | State/County |  | 40.4103 | 74.0432
3 | 400 | Flooding | SR 36 (N) | Many Mind / Wagner Creek | Physical |  | Elevate Roadway, Improve Drainage | Intermediate | 6500000 | State |  | 40.4133 | 74.0521
4 | 410 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 6000000 | County | Not including Harmony Road (below)
4 | 420 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2100 | County
4 | 430 | Capacity | CR 516/ CR 50 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
4 | 440 | Capacity | CR 516/ CR 50 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
4 | 450 | Capacity | CR 516/ CR 50 | Corridor Wide | Physical | NA | Add Evacuation Route signing at key locations | Short | 1600 | County
4 | 460 | Capacity | CR 516/ CR 50 | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | LED and Backup Power for Signals | Intermediate | 28000 | County |  | 40.4146 | 74.0872 | 40.4147 | 74.0947 | 40.4119 | 74.1029
4 | 470 | Capacity | CR 516/ CR 50 | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | Upgrade signals for wireless control | Intermediate | 92000 | County |  | 40.4146 | 74.0872 | 40.4147 | 74.0947 | 40.4119 | 74.1029
4 | 480 | Capacity | CR 516/ CR 50 | Church Street | Operational |  | Close a portion of Church Street in the SB Direction, Install temporary detour signs | During Evacuation | 2000 | Municipality |  | 40.4127 | 74.1013
4 | 490 | Capacity | CR 516/ CR 50 | SR 35 / CR 50 | Physical |  | Widen roadbed between CR 50 and Harmony Road | Long | 1500000 | State/County |  | 40.3963 | 74.1131
4 | 500 | Capacity | CR 516/ CR 50 | Parking Lot, SR 36 | Operational | Ž | Close southerly driveway entrance | During Evacuation | 500 | Municipality |  | 40.3991 | 74.1135
5 | 510 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 12500000 | County
5 | 520 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Physical | NA | Install Coastal Evacuation Route signing throughout route | Short | 4500 | County
5 | 530 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality
5 | 540 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality
5 | 550 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 42000 | County
5 | 560 | Capacity | CR 8A / 12A / 12 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 138000 | County
5 | 570 | Flooding | CR 8A / 12A / 12 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
5 | 580 | Capacity | CR 8A / 12A / 12 | Oceanic Bridge | Physical | Œ | Reconstruct Bridge | Long | 50000000 | County/State/ Federal |  | 40.3813 | 74.014
5 | 590 | Capacity | CR 8A / 12A / 12 | NJ GSP Exit 114 | Operational |  | Close connecting ramp between GSP on-and off ramps; reverse GSP southbound Exit Ramp to Red Hill Rd. | During Evacuation | 8000 | Municipality | Daily | 40.3737 | 74.1482
5 | 600 | Capacity | CR 8A / 12A / 12 | NJ GSP Exit 114 | System Management | Ž | Coordinate GSP ramp reversal activities with NJMCOEM and NJDOT | Short | 0 | MCOEM |  | 40.3737 | 74.1482
6 | 610 | Capacity | CR 520 | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 16500000 | County
6 | 620 | Capacity | CR 520 | Corridor Wide | Operational | NA | Initiate Emergency Service Patrol Program | During Evacuation | 4000 | Municipality | Daily
6 | 630 | Capacity | CR 520 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 70000 | Municipality
6 | 640 | Capacity | CR 520 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 230000 | County
6 | 650 | Capacity | CR 520 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
6 | 660 | Capacity | CR 520 | Rumson Bridge | Physical | Œ | Widen Bridge to 42 feet | Intermediate | 500000 | County |  | 40.3658 | 73.9755
6 | 670 | Capacity | CR 520 | Rumson Bridge | System Management | Œ | Coordinate evacuation planning initiatives with NJTPA activities associated with the Rumson Rd. over Shrewsbury River Study | Short | 0 | MCOEM |  | 40.3658 | 73.9755
6 | 680 | Capacity | CR 520 | Pinckney Road | Physical |  | Add "No Parking During Evacuation" Placards | Short | 6000 | County |  | 40.3408 | 74.0567
6 | 690 | Capacity | CR 520 | Pinckney Road | Operational |  | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily | 40.3408 | 74.0567
6 | 700 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Physical | Ž | Major capital improvement connecting Rumson Rd. and Newman Springs Rd. | Long | 30000000 | County / Municipality / State |  | 40.3375 | 74.0489 | 40.3382 | 74.0637 | 40.3359 | 74.0546
6 | 710 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | System Management | Ž | Coordinate road enhancement program in the vicinity of the Broad Street / SR 35 Intersection. | Intermediate | 0 | County / NJTPA/ State |  | 40.3375 | 74.0489 | 40.3382 | 74.0637 | 40.3359 | 74.0546
6 | 720 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Detour Rumson Rd. WB traffic to White Rd. and SR 35 NB to access Newman Springs Rd. and provide "Alt" Signing | During Evacuation | 2000 | Municipality |  | 40.3375 | 74.0489 | 40.3382 | 74.0637 | 40.3359 | 74.0546
6 | 730 | Capacity | CR 520 | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Upgrade White Rd., as necessary to function as a portal section and install Coastal Evacuation route signs | Long | 1900000 | Municipality |  | 40.3375 | 74.0489 | 40.3382 | 74.0637 | 40.3359 | 74.0546
6 | 740 | Capacity | CR 520 | NJ GSP Exit 109 SB entrance ramp | Physical |  | Construct cross-over ramp section that would connect GSP SB entrance ramp to the GSP SB exit ramp; reverse direction of exit ramp from SB to NB | Intermediate | 198000 | State |  | 40.3365 | 74.1026
6 | 750 | Capacity | CR 520 | NJ GSP Exit 109 SB entrance ramp | Operational |  | Close ramp, provide police enforcement | During Evacuation | 5000 | State | Daily | 40.3365 | 74.1026
6 | 760 | Capacity | CR 520 | NJ GSP Exit 109 | System Management |  | Coordinate GSP ramp reversal activities with NJMCOEM and NJDOT | Short | 0 | State/ MCOEM |  | 40.3365 | 74.1026
7 | 770 | Capacity | SR 36 (Central) | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 14000000 | State
7 | 780 | Capacity | SR 36 (Central) | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 5000 | County with State Approval
7 | 790 | Capacity | SR 36 (Central) | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
7 | 800 | Capacity | SR 36 (Central) | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 4000 | Municipality | Daily
7 | 810 | Capacity | SR 36 (Central) | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 98000 | State
7 | 820 | Capacity | SR 36 (Central) | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 322000 | State
7 | 830 | Capacity | SR 36 (Central) | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
7 | 840 | Capacity | SR 36 (Central) | SR 36 between Clifton Ave. and Washington Street | Physical | Œ | RE-stripe to provide one additional WB lane | Short | 30000 | State |  | 40.3134 | 73.981
7 | 850 | Capacity | SR 36 (Central) | SR 36/Florence Ave. unsignalized intersection | Operational |  | Deploy police resources | During Evacuation | 500 | Municipality | Daily | 40.3132 | 73.9859
7 | 860 | Capacity | SR 36 (Central) | Florence Ave. between MacArthur Ave. and SR 36 | Operational |  | Close Florence Close Florence Ave. SB between MacArthur Way and SR 36 (option to deploying police as above) | During Evacuation | 0 | Municipality |  | 40.3132 | 73.9859
7 | 870 | Capacity | SR 36 (Central) | Bridge over Troutmans Creek | Physical | Ž | Option - Widen Bridge to 42 feet and provide one travel lane and full hard running shoulder in each direction | Long | 44000 | State |  | 40.3125 | 73.9868
7 | 880 | Capacity | SR 36 (Central) | SR 36 connections at Clifton Ave., Long Branch Ave., Liberty St., Rockwell Ave., Seventh Ave., Washington St. | Operational |  | Prohibit left-turn in WB direction; deploy police at each intersection. | During Evacuation | 3000 | Municipality | Daily | 40.306 | 74.0041 | 40.307 | 74.0016
7 | 890 | Capacity | SR 36 (Central) | At-grade RR crossing near Washington St. | System Management |  | Coordinate portal improvements near RR crossing with NJ Transit | Long | 0 | NJ TRANSIT / MCOEM |  | 40.307 | 74.0016 | 40.2908 | 74.0703
7 | 900 | Flooding | SR 36 (Central) | (MP 4.4 to MP5.5 - Long Branch Ave.) | System Management |  | Coordinate this future candidate drainage project with NJ Transit | Long | 0 | STATE / COUNTY/ NJ TRANSIT |  | 40.307 | 74.0016 | 40.2908 | 74.0703
7 | 910 | Capacity | SR 36 (Central) | SR 36 between Branchport Ave. and Victor Ave. | Operational |  | Create two temporary WB lanes using traffic control devices and deployment of police. | During Evacuation | 1000 | MCOEM/ Municipality |  | 40.306 | 74.0041 | 40.307 | 74.0016 | 40.2908 | 74.0703
7 | 920 | Capacity | SR 36 (Central) | SR 36 between Washington St. and Victor Ave. | Operational | ‘ | Narrow grassy median, install third WB travel lane | Long | 5000000 | State |  | 40.2908 | 74.0703
7 | 930 | Capacity | SR 36 (Central) | NJ GSP Exit105 | Operational | ’ | Reverse direction and function of GSP Exit ramp to SR 36 EB; make it an on-ramp to GSP and change its direction from SB to NB | Short | 5000 | State | Daily | 40.2908 | 74.0703
8 | 940 | Capacity | Park Ave. | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 3300000 | County
8 | 950 | Capacity | Park Ave. | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2400 | County
8 | 960 | Capacity | Park Ave. | Corridor Wide | Physical | NA | Install Coastal Evacuation Route signing throughout route | Short | 8000 | County
8 | 970 | Capacity | Park Ave. | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
8 | 980 | Capacity | Park Ave. | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality
8 | 990 | Capacity | Park Ave. | Corridor Wide | Operational | NA | Coordinate Highway Advisory Radio Messages through nearby systems | Short | 0 | MCOEM/ Municipality
8 | 1000 | Capacity | Park Ave. | Corridor Wide | System Management | NA | Where appropriate, coordinate corridor improvements with NJTPA 2030 Plan initiatives | Long | 0 | State/ County/ NJTPA
8 | 1010 | Capacity | Park Ave. | Corridor Wide | System Management | NA | Provide evacuees with emergency information through a public communication program | Short | 0 | MCOEM
8 | 1020 | Capacity | Park Ave. | NJ Coast Line Crossing, West of Lincoln Ave. | System Management | Œ | Coordinate improvements with NJ Transit to account for Evacuation | Long | 0 | County/ NJ Transit |  | 40.2699 | 73.9955
8 | 1030 | Capacity | Park Ave. | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Technological |  | Provide Portable Traffic Signals | Intermediate | 60000 | County/ Municipality |  | 40.2709 | 74.0158 | 40.2695 | 74.0154
8 | 1040 | Capacity | Park Ave. | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Operational |  | Provide police enforcement | During Evacuation | 4000 | Municipality | Daily | 40.2709 | 74.0158 | 40.2695 | 74.0154
8 | 1050 | Capacity | Park Ave. | Corridor Wide | Technological |  | LED and Backup Power for Signals | Intermediate | 35000 | County |  | 40.2709 | 74.0158 | 40.2695 | 74.0154
8 | 1060 | Capacity | Park Ave. | Corridor Wide | Technological |  | Upgrade signals for wireless control | Intermediate | 115000 | County |  | 40.2709 | 74.0158 | 40.2695 | 74.0154
9 | 1070 | Capacity | CR 16 | Corridor Wide | Physical | NA | Widen to create full shoulder | Long | 9000000 | County
9 | 1080 | Capacity | CR 16 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3400 | County
9 | 1090 | Capacity | CR 16 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
9 | 1100 | Capacity | CR 16 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
9 | 1110 | Capacity | CR 16 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 105000 | County/ State
9 | 1120 | Capacity | CR 16 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 345000 | County/ State
9 | 1130 | Capacity | CR 16 | Corridor Wide | System Management | NA | Provide Highway Advisory Radio for this and other nearby corridors | Intermediate | 35000 | MCOEM
9 | 1140 | Capacity | CR 16 | Seaview Sq. Mall entrances to CR 16 | Operational | Œ | Allow only one exit ramp from the mall onto CR 16 | During Evacuation | 5000 | Municipality | Daily | 40.2279 | 74.0456
9 | 1150 | Capacity | CR 16 | Wayside Rd. to Jumping Brook Rd. | Physical |  | Widen State Route 66 | Long | 3800000 | State |  | 40.2296 | 74.0633
9 | 1160 | Capacity | CR 16 | Asbury Park between Essex Rd. and Green Grove Rd. | Operational | Ž | Close business driveways located on south side of Asbury Ave. Provide police enforcement | During Evacuation | 2000 | Municipality | Daily | 40.2344 | 74.0774
9 | 1170 | Capacity | CR 16 | Asbury Ave./Essex Rd. unsignalized intersection | Technological |  | Provide Portable Traffic Signals | Intermediate | 60000 | MCOEM/ Municipality |  | 40.2367 | 74.0817
9 | 1180 | Capacity | CR 16 | Asbury Ave./Essex Rd. unsignalized intersection | Operational |  | Provide police enforcement | During Evacuation | 2000 | Municipality | Daily | 40.2367 | 74.0817
9 | 1190 | Capacity | CR 16 | NJ GSP Exit 102 | Operational |  | Close GSP entrance ramp and reverse direction of GSP exit ramp; provide police enforcement | During Evacuation | 2000 | State | Daily | 40.6706 | 74.0902
9 | 1200 | Capacity | CR 16 | CR 16/Foxchase Drive unsignalized intersection | Operational | ‘ | Provide police enforcement | During Evacuation | 2000 | Municipality | Daily | 40.6707 | 74.0941
9 | 1210 | Capacity | CR 16 | CR 16/CR 547 intersection | Physical | ’ | Widen CR 16 westbound approach to provide full shoulder; also widen intersection's west leg to provide two departure lanes | Long | 500000 | County |  | 40.6803 | 74.1005
10 | 1220 | Capacity | SR 33 | Corridor Wide | Physical | NA | Widen to create full shoulder | Long | 10000000 | State
10 | 1230 | Capacity | SR 33 | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3700 | County with State Approval
10 | 1240 | Capacity | SR 33 | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuations | 2000 | Municipality | Daily
10 | 1250 | Capacity | SR 33 | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuations | 5000 | Municipality | Daily
10 | 1260 | Capacity | SR 33 | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 105000 | State
10 | 1270 | Capacity | SR 33 | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 345000 | State
10 | 1280 | Capacity | SR 33 | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
10 | 1290 | Capacity | SR 33 | Corridor Wide | System Management | NA | Institute public communication program through multi-media sources to provide evacuees with information about emergency shelters | During Evacuation | 0 | MCOEM
10 | 1300 | Capacity | SR 33 | Corridor Wide | Physical | NA | Promote coordination with the new HAR proposed for Neptune in this report. | Intermediate | 0 | MCOEM
10 | 1310 | Capacity | SR 33 | SR 33 WB between Atkins Ave. and Myrtle Ave. | Physical | Œ | Provide second westbound lane thorugh a combination of pavement re-striping, narrowing center median, and realigning sidewalk | Long | 250000 | State |  | 40.2101 | 74.0215
10 | 1320 | Capacity | SR 33 | SR 33 at NJ GSP Exit 100A | Physical |  | Construct crossover between GSP on-ramp and exit ramp | Long | 750000 | State
10 | 1330 | Capacity | SR 33 | SR 33 at NJ GSP Exit 100A | Operational | Ž | Provide police enforcement | During Evacuation | 4000 | Municipality | Daily
11 | 1340 | Capacity | CR 524 (Allaire) | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 7700000 | County
11 | 1350 | Capacity | CR 524 (Allaire) | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3000 | County
11 | 1360 | Capacity | CR 524 (Allaire) | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
11 | 1370 | Capacity | CR 524 (Allaire) | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
11 | 1380 | Capacity | CR 524 (Allaire) | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | LED and Backup Power for Signals | Intermediate | 21000 | County |  | 40.1543 | 74.0549 | 40.1537 | 74.0585 | 40.1525 | 74.0725
11 | 1390 | Capacity | CR 524 (Allaire) | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | Upgrade signals for wireless control | Intermediate | 69000 | State |  | 40.1543 | 74.0549 | 40.1537 | 74.0585 | 40.1525 | 74.0725
11 | 1400 | Capacity | CR 524 (Allaire) | SR 34, between Traffic Circle and Allenwood Rd. | Physical | Ž | Install third travel lane in northbound direction between traffic circle and Allenwood Rd. | Long | 1100000 | State |  | 40.154 | 74.098
11 | 1410 | Capacity | CR 524 (Allaire) | SR 34 Traffic Circle | Physical |  | Convert traffic circle into signalized intersection | Long | 10000000 | Municipality |  | 40.1501 | 74.096
11 | 1420 | Capacity | CR 524 (Allaire) | Cr 524/Allenwood Rd./Ridgewood Rd. | Operational |  | Control traffic flow using police | During Evacuation | 500 | County | Daily | 40.1495 | 74.1024
11 | 1430 | Capacity | CR 524 (Allaire) | Cr 524/Allenwood Rd./Ridgewood Rd. | Technological |  | Install flashing beacons to control traffic flow through intersection | Short | 10000 | County |  | 40.1495 | 74.1024
12 | 1440 | Capacity | CR 524 Spur | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 8800000 | County
12 | 1450 | Capacity | CR 524 Spur | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3200 | County
12 | 1460 | Capacity | CR 524 Spur | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | na
12 | 1470 | Capacity | CR 524 Spur | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
12 | 1480 | Capacity | CR 524 Spur | CR 20 (Broad Street) | Technological | Œ | LED and Backup Power for Signals | Intermediate | 7000 | County |  | 40.1263 | 74.0492
12 | 1490 | Capacity | CR 524 Spur | CR 20 (Broad Street) | Technological | Œ | Upgrade signals for wireless control | Intermediate | 23000 | State |  | 40.1263 | 74.0492
12 | 1500 | Capacity | CR 524 Spur | SR 35/CR 524 Spur Traffic Circle | Physical |  | Eliminate traffic circle | Long | 10000000 | Municipality |  | 40.1324 | 74.0652
12 | 1510 | Capacity | CR 524 Spur | Tilton Corner Road | Operational | Ž | Close road and detour traffic to Ridgewood Road | During Evacuation | 4000 | Municipality | Daily | 40.1411 | 74.0514
12 | 1520 | Capacity | CR 524 Spur | CR 524 Spur at Ramshorn Drive | Operational |  | Deploy police at unsignalized intersection | During Evacuation | 500 | Municipality | Daily | 40.1419 | 74.0666
[6 empty] |  | 140

## POSWRITER
LATITUDE | DEG | 40 | °
| MIN | 8 | '
| SEC | 30.78 | "
LONGITUDE | DEG | 74 | °
| MIN | 3 | '
| SEC | 59.6 | "
|  | 40° 8' 30.78" | 74° 3' 59.6"

## COVER
MONMOUTH COUNTY EVACUATION ROUTE IMPROVEMENT STUDY
APPENDIX F
TREATMENT DATABASE
Route # | Name
1 | CR 39 between Florence Avenue and SR 36,
2 | CR 7/CR 56 between Beachway, Campview Point and SR 36,
3 | SR 36 between Highlands Bridge Over Shrewsbury River and the GSP,
4 | CR 516/CR 50 between SR 36 and SR 35,
5 | CR 8A/12A/12
6 | CR 520 between Ocean Avenue and GSP,
7 | SR 36 (near Oceanport) between the SR 36/CR 57 junction and GSP,
8 | Park Avenue between SR 71 and SR 18,
9 | CR 16 between SR 71 and GSP and SR 66 between CR 16 and SR 33,
10 | SR 33 between SR 71 and SR 34,
11 | CR 524 between SR 71 and I-195 and
12 | CR 524 Spur between SR 71 and I-CR 524.

## TO MAKE TABLES
RouteNO | ORDER KEY | Portal Route | Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment | LOCATION 1 LATITUDE | LOCATION 1 LONGITUDE | LOCATION 2 LATITUDE | LOCATION 2 LONGITUDE | LOCATION 3 LATITUDE | LOCATION 3 LONGITUDE | LOCATION 4 LATITUDE | LOCATION 4 LONGITUDE | LOCATION 5 LATITUDE | LOCATION 5 LONGITUDE
1 | 10 | County Route 39 | Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2400 | County
1 | 20 | County Route 39 | Capacity | Corridor Wide | Physical | NA | Widen to 42 feet | Long | 400000 | County
1 | 30 | County Route 39 | Capacity | Corridor Wide | Physical | NA | Install Coastal Evacuation Route Signs | Short | 1500 | County
1 | 40 | County Route 39 | Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2300 | Municipality | Daily
1 | 50 | County Route 39 | Capacity | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
1 | 60 | County Route 39 | Flooding | Flat Creek Bridge (Bridge R-7) | Physical | Œ | New Bridge | Short | 0 | N/A | Project is Completed | 40° 26' 50.37" | 74° 9' 59.94"
1 | 70 | County Route 39 | Flooding | East Creek | Physical | Ž | Elevate Roadway, Improve Drainage | Long | 10000000 | State |  | 40° 26' 17.86" | 74° 9' 53.03"
1 | 80 | County Route 39 | Capacity | Washington Avenue to SR 36 | Physical |  | Hard Running Shoulder | Intermediate | 50000 | State/County |  | 40° 26' 17.26" | 74° 9' 44.11"
1 | 90 | County Route 39 | Capacity | Washington Avenue to SR 36 | Physical |  | Relocate Utilities | Intermediate | 35000 | State/County |  | 40° 26' 17.26" | 74° 9' 44.11"
1 | 100 | County Route 39 | Capacity | Hemlock Street | Operational |  | Two-phase signal during evacuations. Divert NB Traffic. | During Evacuations | 4000 | County/Local | Daily | 40° 26' 11.28" | 74° 9' 51.74"
1 | 110 | County Route 39 | Flooding | SR 36/Union Ave | Technological |  | LED and Backup Power for Signals | Intermediate | 7000 | State | location | 40° 26' 16.81" | 74° 9' 52.38"
1 | 120 | County Route 39 | Flooding | SR 36/Union Ave | Technological |  | Upgrade signals for wireless control | Intermediate | 23000 | State/County | location | 40° 26' 16.81" | 74° 9' 52.38"
2 | 130 | CR 56/CR 7 | Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 1400 | County/MCOEM
2 | 140 | CR 56/CR 7 | Capacity | Corridor Wide | Physical | NA | Install Coastal Evacuation Route Signing at Critical Intersections | Short | 2000 | County/MCOEM
2 | 150 | CR 56/CR 7 | Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality
2 | 160 | CR 56/CR 7 | Capacity | Corridor Wide | Operational | NA | Coordinate Existing Highway Advisory System | Short | 0 | State/County OEM
2 | 170 | CR 56/CR 7 | Flooding | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
2 | 180 | CR 56/CR 7 | Capacity | Carr Ave | Operational | Œ | Close Circuit Street | During Evacuation | 1000 | Municipality | Daily | 40° 26' 52.75" | 74° 8' 0.45"
2 | 190 | CR 56/CR 7 | Capacity | Carr Ave | Physical |  | Re-stripe | Short | 27000 | County |  | 40° 26' 34.49" | 74° 7' 55.28"
2 | 200 | CR 56/CR 7 | Capacity | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | LED and Backup Power for Signals | Intermediate | 21000 | State/County | Location | 40° 26' 30.36" | 74° 7' 53.41" | 40° 26' 07.52" | 74° 7' 52.61" | 74° 7' 26.71" | 40° 26' 48.29"
2 | 210 | CR 56/CR 7 | Capacity | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | Upgrade signals for wireless control | Intermediate | 69000 | State/County | Location | 40° 26' 07.52" | 74° 7' 53.41" | 40° 26' 07.52" | 74° 7' 52.61" | 74° 7' 26.71" | 40° 26' 48.29"
2 | 220 | CR 56/CR 7 | Capacity | Church St. | Operational |  | Use parking lane as a through street - Police | During Evacuation | 500 | Municipality | Daily | 40° 26' 30.51" | 74° 7' 51.60"
2 | 230 | CR 56/CR 7 | Capacity | Main St./Henry Hudson Bike Trail | Operational |  | Control Crossing Using Police | During Evacuation | 500 | Municipality | Daily | 40° 26' 24.81" | 74° 7' 48.73"
2 | 240 | CR 56/CR 7 | Capacity | Main St./SR 36 | Physical | ‘ | Widen to create full shoulder | Intermediate | 300000 | State |  | 40° 26' 22.25" | 74° 7' 49.36"
2 | 250 | CR 56/CR 7 | Capacity | Main St./SR 36 | Operational | ‘ | Control Crossing Using Police | During Evacuation | 500 | Municipality | Daily | 40° 26' 22.25" | 74° 7' 49.36"
3 | 260 | SR 36 (N) | Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 30000000 | State
3 | 270 | SR 36 (N) | Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 10400 | County with State Approval
3 | 280 | SR 36 (N) | Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
3 | 290 | SR 36 (N) | Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
3 | 300 | SR 36 (N) | Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 154000 | State
3 | 310 | SR 36 (N) | Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 506000 | State
3 | 320 | SR 36 (N) | Capacity | Corridor Wide | Operational | NA | Coordinate Existing Highway Advisory System | Short | 0 | Municipalities with MCOEM
3 | 330 | SR 36 (N) | Capacity | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
3 | 340 | SR 36 (N) | Capacity | Highlands/Sea Bright | Physical | Œ | New Bridge | Under Construction | 0 | State |  | 40° 23' 46.56" | 73° 58' 45.63"
3 | 350 | SR 36 (N) | Capacity | CR8A | Physical |  | Install Dynamic Message Sign | Intermediate | 30000 | State |  | 40° 24' 9.93" | 73° 59' 45.65"
3 | 360 | SR 36 (N) | Capacity | CR 8A | Physical | Ž | Reconfigure Intersection | Long | 170000 | State/County |  | 40° 24' 18.92" | 74° 0' 17.68"
3 | 370 | SR 36 (N) | Capacity | Normandy Road Underpass | Physical | ‘ | Create one-lane bypass under bridge | Intermediate | 600000 | State |  | 40° 24' 59.86" | 74° 4' 12.88"
3 | 380 | SR 36 (N) | Capacity | Broad Street | Physical | ’ | Widen at Intersection | Intermediate | 4000000 | State/County |  | 40° 25' 37.15" | 74° 11' 48.2"
3 | 390 | SR 36 (N) | Flooding | Lupatatong Creek | Physical |  | Elevate Roadway, Improve Drainage | Long | 6500000 | State/County |  | 40° 24' 37.02" | 74° 2' 35.48"
3 | 400 | SR 36 (N) | Flooding | Many Mind / Wagner Creek | Physical |  | Elevate Roadway, Improve Drainage | Intermediate | 6500000 | State |  | 40° 24' 47.86" | 74° 3' 7.39"
4 | 410 | CR 516/ CR 50 | Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 6000000 | County | Not including Harmony Road (below)
4 | 420 | CR 516/ CR 50 | Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2100 | County
4 | 430 | CR 516/ CR 50 | Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
4 | 440 | CR 516/ CR 50 | Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
4 | 450 | CR 516/ CR 50 | Capacity | Corridor Wide | Physical | NA | Add Evacuation Route signing at key locations | Short | 1600 | County
4 | 460 | CR 516/ CR 50 | Capacity | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | LED and Backup Power for Signals | Intermediate | 28000 | County |  | 40° 24' 52.53" | 74° 5' 13.89" | 40° 24' 53.09" | 74° 5' 40.95" | 40° 24' 42.94" | 74° 6' 10.49"
4 | 470 | CR 516/ CR 50 | Capacity | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | Upgrade signals for wireless control | Intermediate | 92000 | County |  | 40° 24' 52.53" | 74° 5' 13.89" | 40° 24' 53.09" | 74° 5' 40.95" | 40° 24' 42.94" | 74° 6' 10.49"
4 | 480 | CR 516/ CR 50 | Capacity | Church Street | Operational |  | Close a portion of Church Street in the SB Direction, Install temporary detour signs | During Evacuation | 2000 | Municipality |  | 40° 24' 45.86" | 74° 6' 4.75"
4 | 490 | CR 516/ CR 50 | Capacity | SR 35 / CR 50 | Physical |  | Widen roadbed between CR 50 and Harmony Road | Long | 1500000 | State/County |  | 40° 23' 46.56" | 74° 6' 47.03"
4 | 500 | CR 516/ CR 50 | Capacity | Parking Lot, SR 36 | Operational | Ž | Close southerly driveway entrance | During Evacuation | 500 | Municipality |  | 40° 23' 56.64" | 74° 6' 48.58"
5 | 510 | CR 8A / 12A / 12 | Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 12500000 | County
5 | 520 | CR 8A / 12A / 12 | Capacity | Corridor Wide | Physical | NA | Install Coastal Evacuation Route signing throughout route | Short | 4500 | County
5 | 530 | CR 8A / 12A / 12 | Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality
5 | 540 | CR 8A / 12A / 12 | Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality
5 | 550 | CR 8A / 12A / 12 | Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 42000 | County
5 | 560 | CR 8A / 12A / 12 | Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 138000 | County
5 | 570 | CR 8A / 12A / 12 | Flooding | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
5 | 580 | CR 8A / 12A / 12 | Capacity | Oceanic Bridge | Physical | Œ | Reconstruct Bridge | Long | 50000000 | County/State/ Federal |  | 40° 22' 52.73" | 74° 0' 50.46"
5 | 590 | CR 8A / 12A / 12 | Capacity | NJ GSP Exit 114 | Operational |  | Close connecting ramp between GSP on-and off ramps; reverse GSP southbound Exit Ramp to Red Hill Rd. | During Evacuation | 8000 | Municipality | Daily | 40° 22' 25.29" | 74° 8' 53.57"
5 | 600 | CR 8A / 12A / 12 | Capacity | NJ GSP Exit 114 | System Management | Ž | Coordinate GSP ramp reversal activities with NJMCOEM and NJDOT | Short | 0 | MCOEM |  | 40° 22' 25.29" | 74° 8' 53.57"
6 | 610 | CR 520 | Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 16500000 | County
6 | 620 | CR 520 | Capacity | Corridor Wide | Operational | NA | Initiate Emergency Service Patrol Program | During Evacuation | 4000 | Municipality | Daily
6 | 630 | CR 520 | Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 70000 | Municipality
6 | 640 | CR 520 | Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 230000 | County
6 | 650 | CR 520 | Capacity | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
6 | 660 | CR 520 | Capacity | Rumson Bridge | Physical | Œ | Reconstruct Bridge | Short | 80000000 | County |  | 40° 21' 56.89" | 73° 58' 31.94"
6 | 670 | CR 520 | Capacity | Rumson Bridge | Operational | Œ | Coordinate with police. Create additional lane using drums. | Short | 0 | MCOEM |  | 40° 21' 56.89" | 73° 58' 31.94"
6 | 680 | CR 520 | Capacity | Pinckney Road | Physical |  | Add "No Parking During Evacuation" Placards | Short | 6000 | County |  | 40° 20' 26.81" | 74° 3' 24.09"
6 | 690 | CR 520 | Capacity | Pinckney Road | Operational |  | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily | 40° 20' 26.81" | 74° 3' 24.09"
6 | 700 | CR 520 | Capacity | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Physical | Ž | Major capital improvement connecting Rumson Rd. and Newman Springs Rd. | Long | 30000000 | County / Municipality / State |  | 40° 20' 14.98" | 74° 2' 56.15" | 40° 20' 17.47" | 74° 3' 49.35" | 40° 20' 9.27" | 74° 3' 16.55"
6 | 710 | CR 520 | Capacity | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | System Management | Ž | Coordinate road enhancement program in the vicinity of the Broad Street / SR 35 Intersection. | Intermediate | 0 | County / NJTPA/ State |  | 40° 20' 14.98" | 74° 2' 56.15" | 40° 20' 17.47" | 74° 3' 49.35" | 40° 20' 9.27" | 74° 3' 16.55"
6 | 720 | CR 520 | Capacity | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Detour Rumson Rd. WB traffic to White Rd. and SR 35 NB to access Newman Springs Rd. and provide "Alt" Signing | During Evacuation | 2000 | Municipality |  | 40° 20' 14.98" | 74° 2' 56.15" | 40° 20' 17.47" | 74° 3' 49.35" | 40° 20' 9.27" | 74° 3' 16.55"
6 | 730 | CR 520 | Capacity | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Upgrade White Rd., as necessary to function as a portal section and install Coastal Evacuation route signs | Long | 1900000 | Municipality |  | 40° 20' 14.98" | 74° 2' 56.15" | 40° 20' 17.47" | 74° 3' 49.35" | 40° 20' 9.27" | 74° 3' 16.55"
6 | 740 | CR 520 | Capacity | NJ GSP Exit 109 SB entrance ramp | Physical |  | Construct cross-over ramp section that would connect GSP SB entrance ramp to the GSP SB exit ramp; reverse direction of exit ramp from SB to NB | Intermediate | 198000 | State |  | 40° 20' 11.44" | 74° 6' 9.24"
6 | 750 | CR 520 | Capacity | NJ GSP Exit 109 SB entrance ramp | Operational |  | Close ramp, provide police enforcement | During Evacuation | 5000 | State | Daily | 40° 20' 11.44" | 74° 6' 9.24"
6 | 760 | CR 520 | Capacity | NJ GSP Exit 109 | System Management |  | Coordinate GSP ramp reversal activities with NJMCOEM and NJDOT | Short | 0 | State/ MCOEM |  | 40° 20' 11.44" | 74° 6' 9.24"
7 | 770 | SR 36 (Central) | Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 14000000 | State
7 | 780 | SR 36 (Central) | Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 5000 | County with State Approval
7 | 790 | SR 36 (Central) | Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
7 | 800 | SR 36 (Central) | Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 4000 | Municipality | Daily
7 | 810 | SR 36 (Central) | Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 98000 | State
7 | 820 | SR 36 (Central) | Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 322000 | State
7 | 830 | SR 36 (Central) | Capacity | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
7 | 840 | SR 36 (Central) | Capacity | SR 36 between Clifton Ave. and Washington Street | Physical | Œ | RE-stripe to provide one additional WB lane | Short | 30000 | State |  | 40° 18' 48.28" | 73° 58' 51.55"
7 | 850 | SR 36 (Central) | Capacity | SR 36/Florence Ave. unsignalized intersection | Operational |  | Deploy police resources | During Evacuation | 500 | Municipality | Daily | 40° 18' 47.64" | 73° 59' 9.29"
7 | 860 | SR 36 (Central) | Capacity | Florence Ave. between MacArthur Ave. and SR 36 | Operational |  | Close Florence Close Florence Ave. SB between MacArthur Way and SR 36 (option to deploying police as above) | During Evacuation | 0 | Municipality |  | 40° 18' 47.64" | 73° 59' 9.29"
7 | 870 | SR 36 (Central) | Capacity | Bridge over Troutmans Creek | Physical | Ž | Option - Widen Bridge to 42 feet and provide one travel lane and full hard running shoulder in each direction | Long | 44000 | State |  | 40° 18' 45.06" | 73° 59' 12.44"
7 | 880 | SR 36 (Central) | Capacity | SR 36 connections at Clifton Ave., Long Branch Ave., Liberty St., Rockwell Ave., Seventh Ave., Washington St. | Operational |  | Prohibit left-turn in WB direction; deploy police at each intersection. | During Evacuation | 3000 | Municipality | Daily | 40° 18' 21.73" | 74° 0' 14.72" | 40° 18' 25.14" | 74° 0' 5.67"
7 | 890 | SR 36 (Central) | Capacity | At-grade RR crossing near Washington St. | System Management |  | Coordinate portal improvements near RR crossing with NJ Transit | Long | 0 | NJ TRANSIT / MCOEM |  | 40° 18' 25.14" | 74° 0' 5.67" | 40° 17' 26.89" | 74° 4' 12.96"
7 | 900 | SR 36 (Central) | Flooding | (MP 4.4 to MP5.5 - Long Branch Ave.) | System Management |  | Coordinate this future candidate drainage project with NJ Transit | Long | 0 | STATE / COUNTY/ NJ TRANSIT |  | 40° 18' 25.14" | 74° 0' 5.67" | 40° 17' 26.89" | 74° 4' 12.96"
7 | 910 | SR 36 (Central) | Capacity | SR 36 between Branchport Ave. and Victor Ave. | Operational |  | Create two temporary WB lanes using traffic control devices and deployment of police. | During Evacuation | 1000 | MCOEM/ Municipality |  | 40° 18' 21.73" | 74° 0' 14.72" | 40° 18' 25.14" | 74° 0' 5.67" | 40° 17' 26.89" | 74° 4' 12.96"
7 | 920 | SR 36 (Central) | Capacity | SR 36 between Washington St. and Victor Ave. | Operational | ‘ | Narrow grassy median, install third WB travel lane | Long | 5000000 | State |  | 40° 17' 26.89" | 74° 4' 12.96"
7 | 930 | SR 36 (Central) | Capacity | NJ GSP Exit105 | Operational | ’ | Reverse direction and function of GSP Exit ramp to SR 36 EB; make it an on-ramp to GSP and change its direction from SB to NB | Short | 5000 | State | Daily | 40° 17' 26.89" | 74° 4' 12.96"
8 | 940 | Park Ave. | Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 3300000 | County
8 | 950 | Park Ave. | Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2400 | County
8 | 960 | Park Ave. | Capacity | Corridor Wide | Physical | NA | Install Coastal Evacuation Route signing throughout route | Short | 8000 | County
8 | 970 | Park Ave. | Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
8 | 980 | Park Ave. | Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality
8 | 990 | Park Ave. | Capacity | Corridor Wide | Operational | NA | Coordinate Highway Advisory Radio Messages through nearby systems | Short | 0 | MCOEM/ Municipality
8 | 1000 | Park Ave. | Capacity | Corridor Wide | System Management | NA | Where appropriate, coordinate corridor improvements with NJTPA 2030 Plan initiatives | Long | 0 | State/ County/ NJTPA
8 | 1010 | Park Ave. | Capacity | Corridor Wide | System Management | NA | Provide evacuees with emergency information through a public communication program | Short | 0 | MCOEM
8 | 1020 | Park Ave. | Capacity | NJ Coast Line Crossing, West of Lincoln Ave. | System Management | Œ | Coordinate improvements with NJ Transit to account for Evacuation | Long | 0 | County/ NJ Transit |  | 40° 16' 11.64" | 73° 59' 43.7"
8 | 1030 | Park Ave. | Capacity | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Technological |  | Provide Portable Traffic Signals | Intermediate | 60000 | County/ Municipality |  | 40° 16' 15.41" | 74° 0' 56.89" | 40° 16' 10.21" | 74° 0' 55.38"
8 | 1040 | Park Ave. | Capacity | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Operational |  | Provide police enforcement | During Evacuation | 4000 | Municipality | Daily | 40° 16' 15.41" | 74° 0' 56.89" | 40° 16' 10.21" | 74° 0' 55.38"
8 | 1050 | Park Ave. | Capacity | Corridor Wide | Technological |  | LED and Backup Power for Signals | Intermediate | 35000 | County |  | 40° 16' 15.41" | 74° 0' 56.89" | 40° 16' 10.21" | 74° 0' 55.38"
8 | 1060 | Park Ave. | Capacity | Corridor Wide | Technological |  | Upgrade signals for wireless control | Intermediate | 115000 | County |  | 40° 16' 15.41" | 74° 0' 56.89" | 40° 16' 10.21" | 74° 0' 55.38"
9 | 1070 | CR 16 | Capacity | Corridor Wide | Physical | NA | Widen to create full shoulder | Long | 9000000 | County
9 | 1080 | CR 16 | Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3400 | County
9 | 1090 | CR 16 | Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
9 | 1100 | CR 16 | Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
9 | 1110 | CR 16 | Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 105000 | County/ State
9 | 1120 | CR 16 | Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 345000 | County/ State
9 | 1130 | CR 16 | Capacity | Corridor Wide | System Management | NA | Provide Highway Advisory Radio for this and other nearby corridors | Intermediate | 35000 | MCOEM
9 | 1140 | CR 16 | Capacity | Seaview Sq. Mall entrances to CR 16 | Operational | Œ | Allow only one exit ramp from the mall onto CR 16 | During Evacuation | 5000 | Municipality | Daily | 40° 13' 40.55" | 74° 2' 44"
9 | 1150 | CR 16 | Capacity | Wayside Rd. to Jumping Brook Rd. | Physical |  | Widen State Route 66 | Long | 3800000 | State |  | 40° 13' 46.41" | 74° 3' 47.88"
9 | 1160 | CR 16 | Capacity | Asbury Park between Essex Rd. and Green Grove Rd. | Operational | Ž | Close business driveways located on south side of Asbury Ave. Provide police enforcement | During Evacuation | 2000 | Municipality | Daily | 40° 14' 3.96" | 74° 4' 38.76"
9 | 1180 | CR 16 | Capacity | Asbury Ave./Essex Rd. unsignalized intersection | Operational |  | Provide police enforcement | During Evacuation | 2000 | Municipality | Daily. Location is to be re-aligned and signalized in the near future. | 40° 14' 12.01" | 74° 4' 54.03"
9 | 1190 | CR 16 | Capacity | NJ GSP Exit 102 | Operational |  | Close GSP entrance ramp and reverse direction of GSP exit ramp; provide police enforcement | During Evacuation | 2000 | State | Daily | 40° 40' 14.26" | 74° 5' 24.89"
9 | 1200 | CR 16 | Capacity | CR 16/Foxchase Drive unsignalized intersection | Operational | ‘ | Provide police enforcement | During Evacuation | 2000 | Municipality | Daily | 40° 40' 14.37" | 74° 5' 38.91"
9 | 1210 | CR 16 | Capacity | CR 16/CR 547 intersection | Physical | ’ | Widen CR 16 westbound approach to provide full shoulder; also widen intersection's west leg to provide two departure lanes | Long | 500000 | County |  | 40° 40' 49.2" | 74° 6' 1.72"
10 | 1220 | SR 33 | Capacity | Corridor Wide | Physical | NA | Widen to create full shoulder | Long | 10000000 | State
10 | 1230 | SR 33 | Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3700 | County with State Approval
10 | 1240 | SR 33 | Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuations | 2000 | Municipality | Daily
10 | 1250 | SR 33 | Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuations | 5000 | Municipality | Daily
10 | 1260 | SR 33 | Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 105000 | State
10 | 1270 | SR 33 | Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 345000 | State
10 | 1280 | SR 33 | Capacity | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
10 | 1290 | SR 33 | Capacity | Corridor Wide | System Management | NA | Institute public communication program through multi-media sources to provide evacuees with information about emergency shelters | During Evacuation | 0 | MCOEM
10 | 1300 | SR 33 | Capacity | Corridor Wide | Physical | NA | Promote coordination with the new HAR proposed for Neptune in this report. | Intermediate | 0 | MCOEM
10 | 1310 | SR 33 | Capacity | SR 33 WB between Atkins Ave. and Myrtle Ave. | Physical | Œ | Provide second westbound lane thorugh a combination of pavement re-striping, narrowing center median, and realigning sidewalk | Long | 250000 | State |  | 40° 12' 36.52" | 74° 1' 17.5"
10 | 1320 | SR 33 | Capacity | SR 33 at NJ GSP Exit 100A | Physical |  | Construct crossover between GSP on-ramp and exit ramp | Long | 750000 | State
10 | 1330 | SR 33 | Capacity | SR 33 at NJ GSP Exit 100A | Operational | Ž | Provide police enforcement | During Evacuation | 4000 | Municipality | Daily
11 | 1340 | CR 524 (Allaire) | Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 7700000 | County
11 | 1350 | CR 524 (Allaire) | Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3000 | County
11 | 1360 | CR 524 (Allaire) | Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
11 | 1370 | CR 524 (Allaire) | Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
11 | 1380 | CR 524 (Allaire) | Capacity | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | LED and Backup Power for Signals | Intermediate | 21000 | County |  | 40° 9' 15.61" | 74° 3' 17.54" | 40° 9' 13.32" | 74° 3' 30.54" | 40° 9' 8.90" | 74° 4' 21.05"
11 | 1390 | CR 524 (Allaire) | Capacity | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | Upgrade signals for wireless control | Intermediate | 69000 | State |  | 40° 9' 15.61" | 74° 3' 17.54" | 40° 9' 13.32" | 74° 3' 30.54" | 40° 9' 8.90" | 74° 4' 21.05"
11 | 1400 | CR 524 (Allaire) | Capacity | SR 34, between Traffic Circle and Allenwood Rd. | Physical | Ž | Install third travel lane in northbound direction between traffic circle and Allenwood Rd. | Long | 1100000 | State |  | 40° 9' 14.43" | 74° 5' 52.94"
11 | 1410 | CR 524 (Allaire) | Capacity | SR 34 Traffic Circle | Physical |  | Convert traffic circle into signalized intersection | Long | 10000000 | Municipality |  | 40° 9' 0.41" | 74° 5' 45.57"
11 | 1420 | CR 524 (Allaire) | Capacity | Cr 524/Allenwood Rd./Ridgewood Rd. | Operational |  | Control traffic flow using police | During Evacuation | 500 | County | Daily | 40° 8' 58.09" | 74° 6' 8.48"
11 | 1430 | CR 524 (Allaire) | Capacity | Cr 524/Allenwood Rd./Ridgewood Rd. | Technological |  | Install flashing beacons to control traffic flow through intersection | Short | 10000 | County |  | 40° 8' 58.09" | 74° 6' 8.48"
12 | 1440 | CR 524 Spur | Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 8800000 | County
12 | 1450 | CR 524 Spur | Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3200 | County
12 | 1460 | CR 524 Spur | Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | na
12 | 1470 | CR 524 Spur | Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
12 | 1480 | CR 524 Spur | Capacity | CR 20 (Broad Street) | Technological | Œ | LED and Backup Power for Signals | Intermediate | 7000 | County |  | 40° 7' 34.61" | 74° 2' 57"
12 | 1490 | CR 524 Spur | Capacity | CR 20 (Broad Street) | Technological | Œ | Upgrade signals for wireless control | Intermediate | 23000 | State |  | 40° 7' 34.61" | 74° 2' 57"
12 | 1500 | CR 524 Spur | Capacity | SR 35/CR 524 Spur Traffic Circle | Physical |  | Eliminate traffic circle | Long | 10000000 | Municipality |  | 40° 7' 56.54" | 74° 3' 54.88"
12 | 1510 | CR 524 Spur | Capacity | Tilton Corner Road | Operational | Ž | Close road and detour traffic to Ridgewood Road | During Evacuation | 4000 | Municipality | Daily | 40° 8' 27.92" | 74° 3' 5.01"
12 | 1520 | CR 524 Spur | Capacity | CR 524 Spur at Ramshorn Drive | Operational |  | Deploy police at unsignalized intersection | During Evacuation | 500 | Municipality | Daily | 40° 8' 30.78" | 74° 3' 59.6"
[6 empty] |  | 140

## CORRHEAD
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment

## CORR01
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2400 | County | 0
Capacity | Corridor Wide | Physical | NA | Widen to 42 feet | Long | 400000 | County | 0
Capacity | Corridor Wide | Physical | NA | Install Coastal Evacuation Route Signs | Short | 1500 | County | 0
Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2300 | Municipality | Daily
Capacity | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM | 0
Flooding | Flat Creek Bridge (Bridge R-7) | Physical | Œ | New Bridge | Short | 0 | N/A | Project is Completed
Flooding | East Creek | Physical | Ž | Elevate Roadway, Improve Drainage | Long | 10000000 | State | 0
Capacity | Washington Avenue to SR 36 | Physical |  | Hard Running Shoulder | Intermediate | 50000 | State/County | 0
Capacity | Washington Avenue to SR 36 | Physical |  | Relocate Utilities | Intermediate | 35000 | State/County | 0
Capacity | Hemlock Street | Operational |  | Two-phase signal during evacuations. Divert NB Traffic. | During Evacuations | 4000 | County/Local | Daily
Flooding | SR 36/Union Ave | Technological |  | LED and Backup Power for Signals | Intermediate | 7000 | State | location
Flooding | SR 36/Union Ave | Technological |  | Upgrade signals for wireless control | Intermediate | 23000 | State/County | location

## CORR02
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 1400 | County/MCOEM
Capacity | Corridor Wide | Physical | NA | Install Coastal Evacuation Route Signing at Critical Intersections | Short | 2000 | County/MCOEM
Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality
Capacity | Corridor Wide | Operational | NA | Coordinate Existing Highway Advisory System | Short | 0 | State/County OEM
Flooding | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
Capacity | Carr Ave | Operational | Œ | Close Circuit Street | During Evacuation | 1000 | Municipality | Daily
Capacity | Carr Ave | Physical |  | Re-stripe | Short | 27000 | County
Capacity | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | LED and Backup Power for Signals | Intermediate | 21000 | State/County | Location
Capacity | Church St., Rt. 36, Pt. Monmouth Rd. | Technological | Ž | Upgrade signals for wireless control | Intermediate | 69000 | State/County | Location
Capacity | Church St. | Operational |  | Use parking lane as a through street - Police | During Evacuation | 500 | Municipality | Daily
Capacity | Main St./Henry Hudson Bike Trail | Operational |  | Control Crossing Using Police | During Evacuation | 500 | Municipality | Daily
Capacity | Main St./SR 36 | Physical | ‘ | Widen to create full shoulder | Intermediate | 300000 | State
Capacity | Main St./SR 36 | Operational | ‘ | Control Crossing Using Police | During Evacuation | 500 | Municipality | Daily

## CORR03
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 30000000 | State
Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 10400 | County with State Approval
Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 154000 | State
Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 506000 | State
Capacity | Corridor Wide | Operational | NA | Coordinate Existing Highway Advisory System | Short | 0 | Municipalities with MCOEM
Capacity | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
Capacity | Highlands/Sea Bright | Physical | Œ | New Bridge | Under Construction | 0 | State
Capacity | CR8A | Physical |  | Install Dynamic Message Sign | Intermediate | 30000 | State
Capacity | CR 8A | Physical | Ž | Reconfigure Intersection | Long | 170000 | State/County
Capacity | Normandy Road Underpass | Physical | ‘ | Create one-lane bypass under bridge | Intermediate | 600000 | State
Capacity | Broad Street | Physical | ’ | Widen at Intersection | Intermediate | 4000000 | State/County
Flooding | Lupatatong Creek | Physical |  | Elevate Roadway, Improve Drainage | Long | 6500000 | State/County
Flooding | Many Mind / Wagner Creek | Physical |  | Elevate Roadway, Improve Drainage | Intermediate | 6500000 | State

## CORR04
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 6000000 | County | Not including Harmony Road (below)
Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2100 | County
Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
Capacity | Corridor Wide | Physical | NA | Add Evacuation Route signing at key locations | Short | 1600 | County
Capacity | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | LED and Backup Power for Signals | Intermediate | 28000 | County
Capacity | East Road, Main Street, Cherry Tree Farm Road | Technological | Œ | Upgrade signals for wireless control | Intermediate | 92000 | County
Capacity | Church Street | Operational |  | Close a portion of Church Street in the SB Direction, Install temporary detour signs | During Evacuation | 2000 | Municipality
Capacity | SR 35 / CR 50 | Physical |  | Widen roadbed between CR 50 and Harmony Road | Long | 1500000 | State/County
Capacity | Parking Lot, SR 36 | Operational | Ž | Close southerly driveway entrance | During Evacuation | 500 | Municipality

## CORR05
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 12500000 | County
Capacity | Corridor Wide | Physical | NA | Install Coastal Evacuation Route signing throughout route | Short | 4500 | County
Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality
Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality
Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 42000 | County
Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 138000 | County
Flooding | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
Capacity | Oceanic Bridge | Physical | Œ | Reconstruct Bridge | Long | 50000000 | County/State/ Federal
Capacity | NJ GSP Exit 114 | Operational |  | Close connecting ramp between GSP on-and off ramps; reverse GSP southbound Exit Ramp to Red Hill Rd. | During Evacuation | 8000 | Municipality | Daily
Capacity | NJ GSP Exit 114 | System Management | Ž | Coordinate GSP ramp reversal activities with NJMCOEM and NJDOT | Short | 0 | MCOEM

## CORR06
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 16500000 | County
Capacity | Corridor Wide | Operational | NA | Initiate Emergency Service Patrol Program | During Evacuation | 4000 | Municipality | Daily
Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 70000 | Municipality
Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 230000 | County
Capacity | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
Capacity | Rumson Bridge | Physical | Œ | Reconstruct Bridge | Short | 80000000 | County
Capacity | Rumson Bridge | Operational | Œ | Coordinate with police. Create additional lane using drums. | Short | 0 | MCOEM
Capacity | Pinckney Road | Physical |  | Add "No Parking During Evacuation" Placards | Short | 6000 | County
Capacity | Pinckney Road | Operational |  | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
Capacity | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Physical | Ž | Major capital improvement connecting Rumson Rd. and Newman Springs Rd. | Long | 30000000 | County / Municipality / State
Capacity | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | System Management | Ž | Coordinate road enhancement program in the vicinity of the Broad Street / SR 35 Intersection. | Intermediate | 0 | County / NJTPA/ State
Capacity | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Detour Rumson Rd. WB traffic to White Rd. and SR 35 NB to access Newman Springs Rd. and provide "Alt" Signing | During Evacuation | 2000 | Municipality
Capacity | CR 520 sections of Branch Ave., Broad St., Pinckney Rd. | Operational | Ž | Upgrade White Rd., as necessary to function as a portal section and install Coastal Evacuation route signs | Long | 1900000 | Municipality
Capacity | NJ GSP Exit 109 SB entrance ramp | Physical |  | Construct cross-over ramp section that would connect GSP SB entrance ramp to the GSP SB exit ramp; reverse direction of exit ramp from SB to NB | Intermediate | 198000 | State
Capacity | NJ GSP Exit 109 SB entrance ramp | Operational |  | Close ramp, provide police enforcement | During Evacuation | 5000 | State | Daily
Capacity | NJ GSP Exit 109 | System Management |  | Coordinate GSP ramp reversal activities with NJMCOEM and NJDOT | Short | 0 | State/ MCOEM

## CORR07
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 14000000 | State
Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 5000 | County with State Approval
Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 4000 | Municipality | Daily
Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 98000 | State
Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 322000 | State
Capacity | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | Short | 0 | MCOEM
Capacity | SR 36 between Clifton Ave. and Washington Street | Physical | Œ | RE-stripe to provide one additional WB lane | Short | 30000 | State
Capacity | SR 36/Florence Ave. unsignalized intersection | Operational |  | Deploy police resources | During Evacuation | 500 | Municipality | Daily
Capacity | Florence Ave. between MacArthur Ave. and SR 36 | Operational |  | Close Florence Close Florence Ave. SB between MacArthur Way and SR 36 (option to deploying police as above) | During Evacuation | 0 | Municipality
Capacity | Bridge over Troutmans Creek | Physical | Ž | Option - Widen Bridge to 42 feet and provide one travel lane and full hard running shoulder in each direction | Long | 44000 | State
Capacity | SR 36 connections at Clifton Ave., Long Branch Ave., Liberty St., Rockwell Ave., Seventh Ave., Washington St. | Operational |  | Prohibit left-turn in WB direction; deploy police at each intersection. | During Evacuation | 3000 | Municipality | Daily
Capacity | At-grade RR crossing near Washington St. | System Management |  | Coordinate portal improvements near RR crossing with NJ Transit | Long | 0 | NJ TRANSIT / MCOEM
Flooding | (MP 4.4 to MP5.5 - Long Branch Ave.) | System Management |  | Coordinate this future candidate drainage project with NJ Transit | Long | 0 | STATE / COUNTY/ NJ TRANSIT
Capacity | SR 36 between Branchport Ave. and Victor Ave. | Operational |  | Create two temporary WB lanes using traffic control devices and deployment of police. | During Evacuation | 1000 | MCOEM/ Municipality
Capacity | SR 36 between Washington St. and Victor Ave. | Operational | ‘ | Narrow grassy median, install third WB travel lane | Long | 5000000 | State
Capacity | NJ GSP Exit105 | Operational | ’ | Reverse direction and function of GSP Exit ramp to SR 36 EB; make it an on-ramp to GSP and change its direction from SB to NB | Short | 5000 | State | Daily

## CORR08
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 3300000 | County
Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 2400 | County
Capacity | Corridor Wide | Physical | NA | Install Coastal Evacuation Route signing throughout route | Short | 8000 | County
Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality
Capacity | Corridor Wide | Operational | NA | Coordinate Highway Advisory Radio Messages through nearby systems | Short | 0 | MCOEM/ Municipality
Capacity | Corridor Wide | System Management | NA | Where appropriate, coordinate corridor improvements with NJTPA 2030 Plan initiatives | Long | 0 | State/ County/ NJTPA
Capacity | Corridor Wide | System Management | NA | Provide evacuees with emergency information through a public communication program | Short | 0 | MCOEM
Capacity | NJ Coast Line Crossing, West of Lincoln Ave. | System Management | Œ | Coordinate improvements with NJ Transit to account for Evacuation | Long | 0 | County/ NJ Transit
Capacity | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Technological |  | Provide Portable Traffic Signals | Intermediate | 60000 | County/ Municipality
Capacity | Park Ave../CR 15 and West Park Ave./CR 15 unsignalized intersections | Operational |  | Provide police enforcement | During Evacuation | 4000 | Municipality | Daily
Capacity | Corridor Wide | Technological |  | LED and Backup Power for Signals | Intermediate | 35000 | County
Capacity | Corridor Wide | Technological |  | Upgrade signals for wireless control | Intermediate | 115000 | County

## CORR09
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Widen to create full shoulder | Long | 9000000 | County
Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3400 | County
Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 105000 | County/ State
Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 345000 | County/ State
Capacity | Corridor Wide | System Management | NA | Provide Highway Advisory Radio for this and other nearby corridors | Intermediate | 35000 | MCOEM
Capacity | Seaview Sq. Mall entrances to CR 16 | Operational | Œ | Allow only one exit ramp from the mall onto CR 16 | During Evacuation | 5000 | Municipality | Daily
Capacity | Wayside Rd. to Jumping Brook Rd. | Physical |  | Widen State Route 66 | Long | 3800000 | State
Capacity | Asbury Park between Essex Rd. and Green Grove Rd. | Operational | Ž | Close business driveways located on south side of Asbury Ave. Provide police enforcement | During Evacuation | 2000 | Municipality | Daily
Capacity | Asbury Ave./Essex Rd. unsignalized intersection | Operational |  | Provide police enforcement | During Evacuation | 2000 | Municipality | Daily. Location is to be re-aligned and signalized in the near future.
Capacity | NJ GSP Exit 102 | Operational |  | Close GSP entrance ramp and reverse direction of GSP exit ramp; provide police enforcement | During Evacuation | 2000 | State | Daily
Capacity | CR 16/Foxchase Drive unsignalized intersection | Operational | ‘ | Provide police enforcement | During Evacuation | 2000 | Municipality | Daily
Capacity | CR 16/CR 547 intersection | Physical | ’ | Widen CR 16 westbound approach to provide full shoulder; also widen intersection's west leg to provide two departure lanes | Long | 500000 | County
Capacity | Corridor Wide | Physical | NA | Widen to create full shoulder | Long | 10000000 | State

## CORR10
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Widen to create full shoulder | Long | 10000000 | State
Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3700 | County with State Approval
Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuations | 2000 | Municipality | Daily
Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuations | 5000 | Municipality | Daily
Capacity | Corridor Wide | Technological | NA | LED and Backup Power for Signals | Intermediate | 105000 | State
Capacity | Corridor Wide | Technological | NA | Upgrade signals for wireless control | Intermediate | 345000 | State
Capacity | Corridor Wide | System Management | NA | Plan to focus on Intense Inundation Areas | During Evacuation | 0 | MCOEM
Capacity | Corridor Wide | System Management | NA | Institute public communication program through multi-media sources to provide evacuees with information about emergency shelters | During Evacuation | 0 | MCOEM
Capacity | Corridor Wide | Physical | NA | Promote coordination with the new HAR proposed for Neptune in this report. | Intermediate | 0 | MCOEM
Capacity | SR 33 WB between Atkins Ave. and Myrtle Ave. | Physical | Œ | Provide second westbound lane thorugh a combination of pavement re-striping, narrowing center median, and realigning sidewalk | Long | 250000 | State
Capacity | SR 33 at NJ GSP Exit 100A | Physical |  | Construct crossover between GSP on-ramp and exit ramp | Long | 750000 | State
Capacity | SR 33 at NJ GSP Exit 100A | Operational | Ž | Provide police enforcement | During Evacuation | 4000 | Municipality | Daily

## CORR11
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 7700000 | County
Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3000 | County
Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | Daily
Capacity | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | LED and Backup Power for Signals | Intermediate | 21000 | County
Capacity | Intersection of CR 524 at SR 35, Warren Ave. and Baily's Corner | Technological | Œ | Upgrade signals for wireless control | Intermediate | 69000 | State
Capacity | SR 34, between Traffic Circle and Allenwood Rd. | Physical | Ž | Install third travel lane in northbound direction between traffic circle and Allenwood Rd. | Long | 1100000 | State
Capacity | SR 34 Traffic Circle | Physical |  | Convert traffic circle into signalized intersection | Long | 10000000 | Municipality
Capacity | Cr 524/Allenwood Rd./Ridgewood Rd. | Operational |  | Control traffic flow using police | During Evacuation | 500 | County | Daily
Capacity | Cr 524/Allenwood Rd./Ridgewood Rd. | Technological |  | Install flashing beacons to control traffic flow through intersection | Short | 10000 | County

## CORR12
Issue | Location | Treatment Category | Map Code | Treatment | Timeframe | Estimated Cost (Not including RoW) | Lead Organization | Comment
Capacity | Corridor Wide | Physical | NA | Widen WB roadway to create a full shoulder | Long | 8800000 | County
Capacity | Corridor Wide | Physical | NA | Add "No Parking During Evacuation" Placards | Short | 3200 | County
Capacity | Corridor Wide | Operational | NA | Enforce "No Parking During Evacuations" | During Evacuation | 2000 | Municipality | na
Capacity | Corridor Wide | Operational | NA | Emergency Service Patrols | During Evacuation | 5000 | Municipality | Daily
Capacity | CR 20 (Broad Street) | Technological | Œ | LED and Backup Power for Signals | Intermediate | 7000 | County
Capacity | CR 20 (Broad Street) | Technological | Œ | Upgrade signals for wireless control | Intermediate | 23000 | State
Capacity | SR 35/CR 524 Spur Traffic Circle | Physical |  | Eliminate traffic circle | Long | 10000000 | Municipality
Capacity | Tilton Corner Road | Operational | Ž | Close road and detour traffic to Ridgewood Road | During Evacuation | 4000 | Municipality | Daily
Capacity | CR 524 Spur at Ramshorn Drive | Operational |  | Deploy police at unsignalized intersection | During Evacuation | 500 | Municipality | Daily